## CRRC SEPTA - Tenco Task Matrix
CRRC Tangshan - SEPTA Cab and Coach Cars Tenco Proposed RMS Scope for CRRC Car
* Project: CRRC - SEPTA Cab and Coach Cars * Base Order includes 34 Coach and 11 Cab cars | [10 empty] | 2019-11-27
CRRC RMS Vehicle Scope Proposed by Tenco
Task Item | CDRL # | TS Section | Work Item | Original Tenco Scope | SEPTA-002 Tenco Scope | SEPTA-003 Tenco Scope | CRRC Scope | Vehicle System Supplier Scope | SEPTA Scope | Staff Hours | Comments / Assumptions
0] Project Management
0.1 |  |  | Project Management | Manage project, coordinate with CRRC and produce monthly Progress Reports. Attend meetings per CRRC request. | Unchanged | Unchanged | Expedite supplier submittals when requested by Tenco. Provide all Subsystem Supplier submittals in scope below for Tenco review. | Respond to Tenco and CRRC requests. | None. | #REF! | Assumes 9 month effort
1] Reliability
1.1 | 02-038 | 2.7 | Reliability Program Plan | Review draft Reliability Program Plan (RPP) | SEPTA approved the RPP on 2/26/2018. No more work on RPP. Supplier RPP: Tenco will work with suppliers to support RAMS deliverables only if directed by the CRRC. No work is presently planned | No work planned. | Revise RPP if requested by SEPTA. Review supplier RPP revisions. | Review and accept RPP, or provide RPP if requested by CRRC. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to RPP. | #REF!
1.2 | 02-038 | 2.7 17.26.2 | Reliability Analysis | Review and further develop Reliability Analysis (RA) and Reliability Prediction per TS 2.7. Review Supplier RAs. Incorporate vehicle level reliability information and Supplier Subsystem RA updates. | CRRC will ask Tenco to assist on an as-needed basis. Supplier RA: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. | Update the RA Report to add conclusions, address SEPTA comments. Attend meetings and provide technical support to CRRC as directed. Review supplier RAs as directed. Does not include incorporation of supplier data into or updating content of RA spreadsheets. | Complete the RA. Enable flow of supplier RA comments and revisions between Tenco and suppliers. Review supplier RA revisions. | Provide subsystem RA and revisions as requested by CRRC along with XLS of analysis. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to RA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 32 or less supplier RA reviews * Trips will be supported by other tasks
1.3 |  | 18.5.7 18.5.8 | Reliability Demonstration Plan | Provide draft Reliability Demonstration Plan (RDP) for Fleet Reliability and Availability Test. Tenco scope does not include Failure Reporting and Corrective Action System (FRACAS) or Reliability Demonstration reporting. Tenco will propose these activities when SEPTA accepts RDP. | CRRC will ask Tenco to assist on an as-needed basis. | Respond to SEPTA RDP comments. Update RDP to address SEPTA comments. Does not include planning for or operation of FRACAS. Does not include participation in the RD. | Review, approve, and submit to SEPTA. | None. | Review and respond to RDP. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 1 additional formal RDP revision * Trips will be supported by other tasks Tenco can propose the necessary FRACAS system work by CRRC request. Scope for Tenco, CRRC, suppliers, and SEPTA may change based on RDP. The level of RD technical support provided by Tenco will be discussed with CRRC when Tenco develops the FRACAS proposal.
2] Maintainability
2.1 | 02-039 | 2.9 | Maintainability Program Plan | Review draft Maintainability Program Plan (MPP). | SEPTA approved the MPP on 4/27/2018. No more work on MPP. Supplier MPP. Tenco will work with suppliers to support RAMS deliverables only if directed by the CRRC. No work is presently planned | No work planned. | Revise MPP if requested by SEPTA. Review supplier MPP revisions. | Review and accept MPP, or provide MPP if requested by CRRC. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to MPP. | #REF!
2.2 |  | 2.8 2.9 | Maintainability and Availability Analyses | Provide draft Maintainability Analyses (MA) and Availability Analysis (AA) including Mean Time To Repair (MTTR), Preventative Maintenance Analysis (PMA) and Corrective Maintenance Analysis (CMA). Review Supplier Subsystem MAs and incorporate into vehicle-level MA. | Tenco will respond to SEPTA MA comments as directed. CRRC will ask Tenco to assist on an as-needed basis. Supplier MA: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. | Respond to SEPTA MA comments. Update the MA Report to add conclusions, address SEPTA comments. Attend meetings and provide technical support to CRRC as directed. Review supplier MAs as directed. Does not include incorporation of supplier data into or updating the content of MA spreadsheets. | Complete the MA. Enable flow of supplier FTAMA comments and revisions between Tenco and suppliers. Review supplier MA revisions. | Provide subsystem MA including MTTR, PMA and CMA, along with XLS of analysis. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to MA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 32 or less supplier MA reviews * Trips will be supported by other tasks
2.3 |  | 2.9 | Maintainability Demonstration Plan | Provide draft Maintainability Demonstration Plan (MDP) Review Supplier Maintainability Demonstration (MD) task lists. | CRRC will ask Tenco to assist on an as-needed basis. | Respond to SEPTA MDP comments. Update the MDP to address SEPTA comments. | CRRC has provided the MD list to Tenco on 3/8/2019. Review, approve, and submit to SEPTA. | Provide MD task list. | Review and respond to MDP. | #REF! | Submit MDP 90 calendar days before Shipment of the first Pilot cars. Proposal does not include Tenco staff to attend MD.
3] Safety Assurance
3.1 | 02-020 | 2.4.1 2.4.12 14.2 | SSPP | Provide draft System Safety Program Plan (SSPP) Includes provisions for SEPTA upgraded software and upgraded portable test equipment software for SEPTA's existing ATC, PTC, MCP, and event recorder systems. Provide CRRC assistance in car design to enable use of SIL 0 software, and additional design support to make SSPP compliant railcar. Document design guidelines per TS. Review Supplier SSPPs. | SEPTA approved the SSPP on 1/24/2018. No more work on SSPP. Supplier SSPP: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned. | No work planned. | Revise SSPP if requested by SEPTA. Review supplier SSPP revisions, approve, and submit to SEPTA. | Review and accept SSPP. Ansaldo provide SSPP for their scope. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Provide SEPTA Safety program documents. Provide SEPTA Software Safety Plan. Review and respond to SSPP. | #REF!
3.2 | 02-021 | 2.4.7 | SDS for Hazardous Materials | Review and compile MSDS provided by CRRC and Subsystem Suppliers. Prepare MSDS for Hazardous Materials submittal. | CRRC will ask Tenco to assist on an as-needed basis. Supplier MSDS: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned | No work planned. | Review supplier MSDS, approve, and submit to SEPTA. Provide MSDS sheets per TS 2.4.7. | Provide MSDS sheets per TS 2.4.7. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to Hazardous Material submittal. | #REF!
3.3 |  | 2.4.3 | FTA | Develop quantitative Fault Tree Analysis (FTA) Review Subsystem Supplier FTAs. | SEPTA conditionally approved the Rev.2 FTA on 7/31/2018. SEPTA stated in March RAMS meeting in Philadelphia that the FTA will need to be updated before final approval. CRRC will ask Tenco to assist on an as-needed basis. Supplier FTA: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned. | Respond to SEPTA comments. Update the FTA to address SEPTA comments, populate failure rates with engineering estimates, update event trees, and add basic event faliure rates from CRRC as available. Attend meetings and provide technical support to CRRC as directed. Review supplier FTAs as directed. | Enable flow of supplier FTA comments and revisions between Tenco and suppliers. Review, approve, and submit to SEPTA. Review supplier FTAs, approve, and submit to SEPTA. | Cab Signal, ATC and Brakes suppliers review and comment on car-level FTA. Door System Supplier provide FTA per CDRL 06-004. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to FTA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 1 additional formal FTA revisions * CRRC will provide FTA Basic Event failure rates * 2 person trips for 1 day / person * 32 or less supplier FTA reviews The FTA Rev 2 is approved by SEPTA. However, Tenco expects, per the RAMS workshop on 3/6/19 in Philadelphia with SEPTA, that SEPTA will require an additional FTA revision. Per TS 2.4.3, "therein unless approved by SEPTA. The Contractor shall develop a quantitative fault tree analysis (FTA) for all Category I and Il severity hazards."
3.4 | 02-022 | 2.4.9 | Preliminary Hazard List | Develop Preliminary Hazard List (PHL). Review Subsystem Supplier PHLs. | SEPTA approved the Rev.2 PHL on 3/24/2018. No more work on PHL. Supplier PHL: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned. | No work planned. | Enable flow of supplier PHL comments and revisions between Tenco and suppliers. | Provide PHL if required by SSPP. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to PHL. | #REF!
3.5 | 02-023 | 2.4.10 | PHA | Develop Preliminary Hazard Analysis (PHA) based on PHL. Review Subsystem Supplier PHAs. | SEPTA approved the Rev.1 PHA on 7/31/2018. No more work on PHA. Supplier PHA: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned. | Review supplier PHAs as directed. | Enable flow of supplier PHA comments and revisions between Tenco and suppliers. | Provide PHA if required by SSPP. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to PHA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 3 or less supplier PHA reviews
3.6 | 02-024 | 2.4.10 | Hazard Tracking Log | Develop Hazard Tracking Log (HTL) | CRRC will ask Tenco to assist on an as-needed basis. Supplier HTL: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned | Respond to SEPTA comments. Update the HTL to address SEPTA comments, add/remove hazards, and update hazard effects and mitigations to reflect SEPTA input and latest design information. Attend meetings and provide technical support to CRRC as directed. Review supplier HTLs as directed. Does not include adding or verifying Verifiable Closure References (VCRs). Add and verify Verifiable Closure References(VCRS) by CRRC direcion. | Add, verify, and maintain VCRs. Enable flow of supplier HTL comments and revisions between Tenco and suppliers. Review, complete, approve, and submit to SEPTA. Review supplier HTL revisions. | Provide HTL if required by SSPP. Provide verifiable closure references by CRRC request. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to HTL. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 3 or less supplier HTL reviews * 3 trips for 2 persons for 2 days each * 3 additional formal HTL revisions Per TS 2.4.10: "The HTL shall be updated and submitted every 90 days after CDR for review." The HTL is the primary tool for Safety Certification, identifying: • All Cat I and II hazards, and Cat III A & B hazards • Mitigations and evidence of closure
3.7 | 01-018 | 1.6.6.2.8 | CFR and APTA Compliance Matrix | Develop CFR and APTA Compliance Matrix for Tenco scope. | CRRC will ask Tenco to assist on an as-needed basis. | No work planned. | Review, complete, approve, and submit to SEPTA. | None. | Review and respond to CFR and APTA Compliance Matrix | #REF!
3.8 | 02-025 | 2.4.11 | Safety Certification Report (SCR) | Draft Safety Certification before revenue service listing open HTL and restrictions | Tenco submitted the SCR to CRRC on 3/19/2019. Tenco will respond to comments and update the SCR as directed by CRRC. | Respond to SEPTA comments. Update the SCR to address SEPTA comments. | Safety Cert Process to be implemented by CRRC and SEPTA staff. Provide all supporting documents not generated by Tenco. Review, approve, and submit to SEPTA. | Provide verifiable reference documents as requested by CRRC. | Safety Cert Process to be implemented by CRRC and SEPTA staff. Review and respond to Safety Certification | #REF! | Per TS 2.4.11: "This safety certification shall include a list of any open items from the HTL and any restrictions in operation."
3.9 | 02-026 | 2.4.11 | Safety Certification Package | Compile Safety Certification Package with all supporting documents (FMECA, FTA, etc…) | No longer required per meeting with SEPTA 7/2 and 7/3. This deliverable is a combination of the completed HTL and the Safety Certification. | No work planned. | Provide all supporting documents not generated by Tenco. Review, approve, and submit to SEPTA. | Provide verifiable reference documents as requested by CRRC. | Review and respond to Safety Certification | #REF!
3.10 | 17-054 17-056 | 2.4.12 17.30.3.1.2 | SQAP | Provide draft car-level Software Quality Assurance Plan (SQAP). The plan shall include the submittal and approval of the following documents: a. System Functional Description (SFD) b. Software Requirements Specification (SRS) in accordance with ANSI/IEEE Standard 830 c. Software Design Description (SDD) in accordance with ANSI/IEEE Standard 1016 d. Software Verification and Validation Plan (SVVP) e. Software Verification and Validation Report (SVVR) f. Software Configuration Management Plan (SCMP) g. User Documentation h. Software System Functional Description (SSFD) | CRRC will ask Tenco to assist on an as-needed basis. Supplier Software Quality deliverables: Tenco will work with suppliers to support RAMS deliverables only if directed by CRRC. No work is presently planned. | No work planned. | Review supplier software documentation, approve, and submit to SEPTA. Review, approve, and submit to SEPTA. Review supplier software quality revisions. | Review and accept SQAP. Provide required Supplier Software Quality Documentation as required by TS 17.30.3 and the SQAP. Respond to CRRC comments, and provide revisions, as necessary. | Provide SEPTA Software Safety Plan. Review and respond to SQAP. | #REF!
3.11 |  | 2.4.12 | SVVP | Provide draft car-level Software Validation and Verification Plan (SVVP) | CRRC will ask Tenco to assist on an as-needed basis. | No work planned. | Review, approve, and submit to SEPTA. | Review and accept SVVP. Provide required Supplier Software Quality Documentation. | Provide SEPTA Software Safety Plan. Review and respond to SVVP. | #REF!
3.12 | 17-054 17-055 | 17.30.3 17.30.3.1.1 | Non-Commercially Available Software review. | Review Supplier submittals for the following: a. System Functional Description (SFD) b. Software Requirements Specification (SRS) in accordance with ANSI/IEEE Standard 830 c. Software Design Description (SDD) in accordance with ANSI/IEEE Standard 1016 d. Software Verification and Validation Plan (SVVP) e. Software Verification and Validation Report (SVVR) f. Software Configuration Management Plan (SCMP) g. User Documentation h. Software System Functional Description (SSFD) Review car-level Software System Functional Description (SSFD) per CDRL 17-055 | No work is presently planned. Review of supplier Software Quality submittals removed from Tenco scope by CRRC on 10/20/2018. | No work planned. | Provide car-level Software System Functional Description (SSFD) per CDRL 17-055. Review, approve, and submit to SEPTA. Review supplier software documentation, approve, and submit to SEPTA. | Provide certification and/or substantiation of Subsystem equipment SIL level if requested by CRRC. Provide or make available for review, software submittals for Safety Critical Software. Provide the following per car-level SQAP and SVVP: a. System Functional Description (SFD) b. Software Requirements Specification (SRS) in accordance with ANSI/IEEE Standard 830 c. Software Design Description (SDD) in accordance with ANSI/IEEE Standard 1016 d. Software Verification and Validation Plan (SVVP) e. Software Verification and Validation Report (SVVR) f. Software Configuration Management Plan (SCMP) g. User Documentation h. Software System Functional Description (SSFD) Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to submitted Supplier Software Quality documentation. | #REF!
3.13 | 02-027 | 2.4.13 | Safety Analyses (SA) | Develop Safety Analyses (SA) per 49 CFR 229 Subpart E and Appendix F. The SA shall: (1) establish and document the minimum requirements that will govern the development and implementation of all products subject to this subpart, and be based on good engineering practice and should be consistent with the guidance contained in appendix F of this part in order to establish that a product’s safety-critical functions will operate with a high degree of confidence in a fail-safe manner; (2) Include procedures for immediate repair of safety-critical functions; and (3) Be made available to FRA upon request. | Tenco submitted the SA Report to CRRC on 3/31/2019. Tenco will respond to comments and update the SA as directed by CRRC. | Respond to SEPTA comments. Update the SA Report to address SEPTA comments. | After Tenco provides the draft SA report body, CRRC completes the SA and submits to SEPTA. Provide vehicle design information, as requested by Tenco. Review, approve, and submit to SEPTA. | Cab Signal, ATC and Brakes suppliers provide support and analyses as requested, including ICD, FMECAs, FTAs, etc. | Review and respond to SA. | #REF! | Tenco Interpretation. The SA requirement could be fulfilled by the RAMS and EMI scope supplemented by HTL showing verifiable reference documents, including: a. Product testing results and record b. Operations and maintenance manuals c. Training and qualification program d. Operating personnel training
3.14 |  | 2.4.7 2.4.8 2.5 | O&SHA | Develop Operating and Support Hazard Analysis (O&SHA) including maintenance errors. Review Subsystem Supplier O&SHAs. | CRRC will ask Tenco to assist on an as-needed basis. Supplier O&SHA: Tenco will work with suppliers to support RAMS deliverables only if directed by the CRRC. No work is presently planned | Respond to SEPTA comments. Update the O&SHA to address SEPTA comments and update condition effects and resolutions to reflect latest design and operation information. Attend meetings and provide technical support to CRRC as directed. Review supplier O&SHAs as directed. Does not include adding or verifying VCRs. Add and verify VCRs by CRRC direction. | Update the O&SHA with verifiable closure references and manuals. Review, complete, approve, and submit to SEPTA. Review supplier O&SHAs, approve, and submit to SEPTA. | Provide verifiable closure references and manuals. Provide O&SHA if required by SSPP. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to O&SHA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 1 additional formal O&SHA revision * Trips will be supported by other tasks * 3 or less supplier O&SHA reviews
3.15 | 02-029 | 2.5 | FMEAs with Preliminary, Subsystem, and System Hazard Lists. | Develop FMEAs for Hazards falling into severity Categories I, II, and III (as defined in MIL-STD-882E). Hazards shall be compiled into a preliminary hazard list (PHL), subsystem hazard list (SSHL), and system hazard list (SHL) including: a. Emergency brakes fail to apply when requested b. Service brakes fail to apply when requested c. Propulsion fails to cease when requested d. No motion detection system indicates no motion when train is moving e. Door opens spontaneously when not commanded f. Door opens on wrong side of car g. Door closes on person's limb and indicates door closed and locked to the control system h. Door interlocks erroneously indicate door is closed and locked i. Excessive currents or overheated equipment cause fire hazard j. Indication of uncoupled when not uncoupled k. Train moves in wrong direction l. Slide control does not reapply brakes after slide correction m. Cars in train separate when not commanded n. Train regenerates into dead section of catenary. Review Subsystem Supplier FMECAs. | Tenco submitted the FMECA Rev 1 to CRRC on 3/15/19. Tenco will respond to comments and update the FMECA as directed by CRRC. Supplier FMECA: Tenco will work with suppliers to support RAMS deliverables only if directed by the CRRC. | Respond to SEPTA comments. Update the FMECA to address SEPTA comments. Update the FMECA to reflect design changes, including those indicated in Car-level Schematic updates. Attend meetings and provide technical support to CRRC as directed. Review supplier FMECAs as directed. Does not include incorporation of failure rates into FMECA. Does not include adding or verifying VCRs. Add and verify VCRs by CRRC direction. | CRRC will populate FMECA line item failure rates. CRRC will inform Tenco of design document updates and provide all required design documents. Review, complete, approve, and submit to SEPTA. Review supplier FMECA revisions. | Provide verifiable closure references and manuals. Provide FMECA if required by SSPP. Respond to CRRC and Tenco comments, and provide revisions, as necessary. | Review and respond to FMEAs. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 2 additional formal FMECA revisions * CRRC will populate FMECA line item failure rates * 2 trips for 2 persons for 2 days each * 3 or less supplier FMECA reviews Estimate is based on updating to Rev E Schematics.
3.16 | 02-030 | 2.5 | Electrical Circuit Failure Mode Analysis Methods | Develop safety analysis methods for electrical circuit failure mode analyses including sneak circuit and dry contact analysis. | Tenco submitted the SCA to CRRC on 3/31/2019. Tenco will respond to comments and update the SCA as directed by CRRC. | Respond to SEPTA comments. Update the SCA to address SEPTA comments. Update the SCA to reflect design changes, including those indicated in Car-level Schematic updates. Attend meetings and provide technical support to CRRC as directed. | CRRC will inform Tenco of design document updates and provide all required design documents. Review, approve, and submit to SEPTA. | Provide information as requested by CRRC and Tenco. | Review and respond to proposed Electrical Circuit Failure Mode Analysis Methods. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 2 additional formal SCA revisions * Trips will be supported by other tasks Estimate is based on updating to Rev E Schematics. TS: "Standard failure and safety analysis methods and published failure rates for components shall be utilized wherever possible. All electrical circuit failure mode analyses shall include a sneak circuit and dry contact analysis. All methods shall be submitted to the Engineer for review and approval."
3.17 | 02-029 02-030 | 2.4.10 2.5 8.2.2 (HVAC) 14.2 (PTC/ATC) | SSHA | Develop Subsystem Hazard Analyses (SSHA) which may include: • Zero Speed • Door Summary Circuit • Emergency Brake • Overspeed • Power loss scenarios of HVAC • 480V Head End Power (HEP) Loop • Trainlines, PTC interfaces and targeted FMECA • Event Recorder Interface | Tenco needs to provide the ATC/PTC and Event Recorder interface analysis due to FRA relationship. Tenco will resume work on the ATC/PTC and Event Recorder interface analysis when directed by CRRC. Tenco will conduct other SSHA work as directed by CRRC. | No work planned. Complete all planned SSHAs. Respond to SEPTA comments. Update the SSHAs to address SEPTA comments. Attend meetings and provide technical support to CRRC as directed. | CRRC will inform Tenco of design document updates and provide all required design documents. Review, approve, and submit to SEPTA. | Provide information as requested by CRRC and Tenco. | Provide fleet information on locomotives and existing coach cars, especially trainlines. Review and respond to SSHA. | #REF! | Assumptions for SEPTA-003 Tenco Scope: * 2 formal revisions for each SSHA * 2 trips for 2 persons for 2 days each Estimate is based on using Rev E Schematics.
3.18 |  | 14.2 (PTC/ATC) | PTC Safety Assessment |  | The ATC/PTC system is the responsibility of SEPTA. No work is presently planned. | No work planned. | None. | PTC supplier to provide information as requested by CRRC and Tenco. | Provide PTC information as requested by CRRC and Tenco. | #REF!
3.19 |  |  | Car-level Schematic Review |  | No work is presently planned. | No work planned. | None. | None. | None. | #REF!
3.20 |  |  | Trainline Definition |  | No work is presently planned. | No work planned. | None. | None. | Provide Trainline configuration information as requested by CRRC and Tenco. | #REF!
4] Life Cycle Cost Evaluation
4.1 |  | No TS requirements stated. Waiting for information from CRRC. | LCC Evaluation | Provide simple draft Life Cycle Cost Evaluation (LCC) considering the typical categories of rail transit costs: * Capital Cost (Procurement Contract Cost) * Operation (Incremental costs only compared to other coaches) * Maintenance (based on PMA and CMA) * Recycling and disposal. | No work is presently planned. Planned report removed from Tenco scope by CRRC on 10/20/2018. | No work planned. | None. |  |  | #REF!
Notes: 1] The Tenco planned scope and estimate is in response to CRRC instructions. It is not linked to Tenco work estimates to complete the project. 2] The estimate does not include contingency. 3] Tenco will provide all draft plans and reports in English. 4] Tenco SEPTA-003 budget applies to the scope as constrained by the assumptions noted in the Task Matrix.
|  |  |  | Estimated Total Man-Hours to Complete Tenco Work Scope: |  |  | #REF!
|  |  |  | Estimated Total Cost to Complete Tenco Work Scope: |  |  | #REF!