## Scope
|  | Hyundai Rotem NYCT Propulsion and APS Loan Agreement Turner Engineering Corporation Proposal for Technical and Project Support Proposed Scope |  |  |  | 2024-07-26
Terms: Tenco proposes to perform the work on a time and material basis, at our engineering service rates in effect at the time. This proposal provides Tenco's estimated typical level of effort to provide the Tenco scope and deliverables listed, subject to the stated assumptions. Factors outside of Tenco's control can affect the actual level of effort. Tenco will inform Hyundai Rotem of any condition which will cause the actual effort to exceed the estimate for that portion of the work. Hyundai Rotem may allocate contingency funding for unknown conditions.
Line Item | Group | Task | Title | Tenco Scope | Hyundai Rotem Scope | Comments/Assumptions
| Loan Agreement Foundation Documents | 1 | Loan Agreement Foundation Documents
1 | Loan Agreement Foundation Documents | 1.1 | Quality Control Program Manual | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions. | This deliverable is required by the Propulsion Loan Agreement only. However, we suggest that both the Propulsion and APS systems should follow the same QCPM.
2 | Loan Agreement Foundation Documents | 1.2 | Electromagnetic Compatibility Plan | Develop EMCP to meet NYCT Loan Agreement and TS requirements | Provide example HR EMCPs. Work with Tenco during EMCP development. Review for compatibility with HR processes and capabilities. | This deliverable is required by both the Propulsion and APS Loan Agreements. However, we suggest both systems should follow the same EMCP.
3 | Loan Agreement Foundation Documents | 1.3 | Smoke Flame Toxicity (SFT) Compliance Plan | Develop and SFT Compliance Plan to guide the design and component selection for compliance. |  | SFT compliance is only required for the APS Loan Agreement. However, we suggest that Hyundai Rotem use the same plan for both APS and Propulsion to ensure that a qualified propulsion system does not have any dependencies on SFT non-compliant components.
4 | Loan Agreement Foundation Documents | 1.4 | Loan Agreement Project Cybersecurity Plan | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions. | Assume that Hyundai Rotem has enterprise cybersecurity policies in place that are generally responsive to the NYCT cybersecurity requirements.
5 | Loan Agreement Foundation Documents | 1.5 | Propulsion and APS Technical Cybersecurity Plan | Develop a technical Cybersecurity plan compliant with the NYCT “MTA Cybersecurity Terms and Conditions (Short Form) with MTA Cyber Requirements,” R160 TS, and R211 TS. | Review for compatibility with HR processes and capabilities. Execute the technical design in compliance with the plan.
88 | Loan Agreement Foundation Documents | 1.6 | Cybersecurity Design Principles | Develop a set of Cybersecurity Design Principles compliant with the NYCT “MTA Cybersecurity Terms and Conditions (Short Form) with MTA Cyber Requirements,” R160 TS, and R211 TS. | Review for compatibility with HR processes and capabilities. Execute the technical design in compliance with the design principles. | Deliverable will be a section of the Technical Cybersecurity Plan
6 | Propulsion | 2 | Propulsion
7 | Propulsion | 2.1 | Propulsion System Qualification Questionnaire | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
8 | Propulsion | 2.2 | Propulsion System Functional Description (SFD) | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
9 | Propulsion | 2.3 | Propulsion System Software Requirements Specifications (SRS) | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
10 | Propulsion | 2.4 | Software Design Description, per R211 TS Section 18.0 | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
11 | Propulsion | 2.5 | Propulsion Equipment Drawings and Schematics | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
12 | Propulsion | 2.6 | Propulsion Loan Agreement Test Plan | Create a Propulsion Loan Agreement Test Plan using the content developed during the Propulsion Requirements Allocation and Traceability Workshop. | Review for compatibility with HR processes and capabilities. | The Loan Agreement uses the word "plan" where "procedure" seems more consistent with the R211 TS terms. We suggest asking for clarification. Regardless, Tenco suggests that an overarching Propulsion Loan Agreement Test Plan will work to define test deliverables and expectations.
13 | Propulsion | 2.7 | EMI Lab Test Plans | Tenco will provide this within the EMCP.
14 | Propulsion | 2.8 | Propulsion EMC Lab Test Procedure | Develop an EMC Lab Test Procedure compliant with the NYCT Loan Agreement and TS requirements and compatible with Hyundai Rotem's designated test laboratory. | Provide examples of past HR EMI test procedures. Collaborate with Tenco during EMC Test Procedure development. Review for compatibility with HR processes and capabilities. | on 19-June Hyundai noted that EMC testing will be at a third-party lab.
15 | Propulsion | 2.9 | Propulsion EMC Lab Test | Support EMC test setup at the third party test lab. Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No Hyundai Rotem internal test before the NYCT witness test. * Tenco assistance with lab preparation
16 | Propulsion | 2.10 | Propulsion EMC Lab Test Report | Develop the EMC Lab Test Report. | Provide a submittal quality report of all test data.
17 | Propulsion | 2.11 | Shock and vibration validation test plan | Included elsewhere |  | Tenco suggests that this Loan Agreement requirement be included in the Propulsion Loan Agreement Test Plan.
18 | Propulsion | 2.12 | Propulsion Inverter Shock and Vibration Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
19 | Propulsion | 2.13 | Propulsion Inverter Shock and Vibration Test | Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No HR internal test before the NYCT witness test. * Test in Seoul.
20 | Propulsion | 2.14 | Propulsion Inverter Shock and Vibration Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
21 | Propulsion | 2.15 | Preliminary Weight Analysis | Review Hyundai Rotem created content and suggest revisions. Assist with weight optimization. | Create first draft and revise to incorporate Tenco's suggestions.
22 | Propulsion | 2.16 | Propulsion Reliability Analysis and Prediction | Develop a Reliability Analysis and Prediction compliant with the NYCT Loan Agreement and R211 TS requirements | Provide technical details needed to create the analysis. Collaborate with Tenco to revise the equipment design to comply with NYCT requirements if necessary. | Assumes HR has accurate reliability information from past projects.
23 | Propulsion | 2.17 | Propulsion Failure Mode, Effects, and Criticality Analysis (FMECA) | Develop a FMECA compliant with the NYCT Loan Agreement and R211 TS requirements | Provide a FMECA from the past APS design used as the Loan Agreement equipment basis. Provide technical details needed to create the analysis. Collaborate with Tenco to revise the equipment design to comply with NYCT requirements if necessary. | Existing FMECA available as a starting point. Developing a full FMECA from a blank sheet will be a much larger effort. The APS Loan Agreement also requires an EMI FMECA. Tenco assumes this will be included in the main propulsion system FMECA.
24 | Propulsion | 2.18 | Test plans for all items listed in R211 TS section 10.7 “Deliverables” | Included elsewhere |  | The scope and intent of this NYCT Loan Agreement requirement is not clear. Many items in TS 10.7 are not "testable". We suggest addressing this during the Commercial Risk Management Task.
25 | Propulsion | 2.19 | Compliance program, per R211 TS 19.0 Materials and Workmanship | Included elsewhere |  | The scope and intent of this Loan Agreement requirement are unclear. Tenco suggests identifying relevant R211 TS 19.0 requirements as part of the Commercial Risk Management Task
26 | Propulsion | 2.20 | Traction Motor Qualification Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
27 | Propulsion | 2.21 | Traction Motor Qualification Test | Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No HR internal test before the NYCT witness test.
28 | Propulsion | 2.22 | Traction Motor Qualification Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
29 | Propulsion | 2.23 | Gear Unit Qualification Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
30 | Propulsion | 2.24 | Gear Unit Qualification Test | Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No HR internal test before the NYCT witness test.
31 | Propulsion | 2.25 | Gear Unit Qualification Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
32 | Propulsion | 2.26 | Power Lab Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
33 | Propulsion | 2.27 | Power Lab Test | Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No HR internal test before the NYCT witness test.
34 | Propulsion | 2.28 | Power Lab Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
35 | Propulsion | 2.29 | Traction Motor Routine Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
36 | Propulsion | 2.30 | Traction Motor Routine Test | None
37 | Propulsion | 2.31 | Traction Motor Routine Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
38 | Propulsion | 2.32 | Gear Unit Routine Test Procedure | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
39 | Propulsion | 2.33 | Gear Unit Routine Test | None
40 | Propulsion | 2.34 | Gear Unit Routine Test Report | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
41 | Propulsion | 2.37 | Propulsion SFT Compliance Audit | Audit SFT documentation for completeness and compliance to the SFT Compliance Plan and NYCT requirements. | Coordinate with suppliers to obtain TS compliant SFT test results. This may require testing. | Although not a Propulsion Loan Agreement requirement, we suggest HR design for SFT compliance.
42 | Propulsion | 2.38 | Propulsion Cybersecurity Plan Compliance Review | Include Cybersecurity review in all Tenco Propulsion Scope.
86 | Propulsion | 2.39 | Propulsion Compliance Auditing | Audit Hyundai Rotem's compliance tracking database. Spot check of 10% of the total compliance items tracked, selected at random. | Develop and maintain a compliance tracking database | Assumes that Hyundai Rotem has an established compliance tracking system.
43 | APS | 3 | APS
44 | APS | 3.1 | Drawings showing installation of the APS on R160 vehicles | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
45 | APS | 3.2 | Electrical interface drawings and wiring diagrams between the APS and the R160 vehicle | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
46 | APS | 3.3 | Final assembly drawings | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
47 | APS | 3.4 | APS System Functional Description | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
48 | APS | 3.5 | APS Loan Agreement Test Plan | Create a APS Loan Agreement Test Plan using the content developed during the APS Requirements Allocation and Traceability Workshop. | Review for compatibility with HR processes and capabilities. | The Loan Agreement uses the word "plan" where "procedure" seems more consistent with the R160 TS terms. We suggest asking for clarification. Regardless, Tenco suggests that an top-level APS Loan Agreement Test Plan should define test deliverables and expectations.
49 | APS | 3.6 | EMC/EMI Lab and Field Test Plans | Included in the APS Loan Agreement Test Plan |  | The wording of the Loan Agreement implies separate plans, however we suggest that a combined lab and field test plan allows for a better integrated test plan, and would be acceptable to NYCT.
50 | APS | 3.7 | Software Design Description, per R160 TS Section 16.0 and MTA Cybersecurity Requirements | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
51 | APS | 3.8 | Portable Test Equipment (PTE) Description | Review Hyundai Rotem created content and suggest revisions. | Create first draft and revise to incorporate Tenco's suggestions.
52 | APS | 3.9 | List of estimated spare components available after the installation is completed | TBD |  | The intent of this NYCT Loan Agreement requirement is not clear. We suggest asking for clarification.
53 | APS | 3.10 | APS Failure Mode, Effects, and Criticality Analysis (FMECA) | Develop a FMECA compliant with the NYCT Loan Agreement and R160 TS requirements | Provide a FMECA from the past APS design used as the Loan Agreement equipment basis. Provide technical details needed to create the analysis. Collaborate with Tenco to revise the equipment design to comply with NYCT requirements if necessary. | Assumes existing FMECA is available as a starting point. Developing a full FMECA from a blank sheet will be a larger effort.
54 | APS | 3.11 | APS EMI FMECA | Included in the main APS FMECA |  | We suggest combining this with the main FMECA.
55 | APS | 3.12 | Material Safety Data Sheets (MSDS) for all adhesive solvents and materials needed to install the APS. | TBD | TBD | The scope and intent of this NYCT Loan Agreement requirement is not clear. We suggest asking for clarification.
56 | APS | 3.13 | Smoke Flame and Toxicity (SFT) compliance certifications for the APS per R160 TS. | Audit SFT documentation for completeness and compliance to the SFT Compliance Plan and NYCT requirements. | Coordinate with suppliers to obtain TS compliant SFT test results. This may require testing. Assemble SFT compliance matrix and supporting documentation.
57 | APS | 3.14 | APS EMC Lab Test Procedure | Develop an EMC Lab Test Procedure compliant with the NYCT Loan Agreement and TS requirements and compatible with Hyundai Rotem's designated test laboratory. | Provide examples of past HR EMI test procedures. Collaborate with Tenco during EMC Test Procedure development. Review for compatibility with HR processes and capabilities. | on 19-June Hyundai noted that EMC testing will be at a third-party lab.
58 | APS | 3.15 | APS EMC Lab Test | Support EMC test setup at the third party test lab. Interface with and assist in managing the NYCT witness' participation and expectations. |  | Assumes: * NYCT will witness the test. * No Hyundai Rotem internal test before the NYCT witness test. * Tenco assistance with lab preparation
59 | APS | 3.16 | APS EMC Lab Test Report | Develop the EMC Lab Test Report. | Provide a submittal quality report of all test data. | Assumes: * Draft for Hyundai Rotem review * Submittal to NYCT version * One revision to respond to NYCT comments.
60 | APS | 3.17 | APS EMC Field Test Procedure | Develop an EMC Field Test Procedure compliant with the NYCT Loan Agreement and TS requirements and compatible with Hyundai Rotem's designated test laboratory. | Provide examples of past HR EMI test procedures. Collaborate with Tenco during EMC Test Procedure development. Review for compatibility with HR processes and capabilities. | Assumes the test will be conducted in New York by Tenco and Hyundai Rotem
61 | APS | 3.18 | APS EMC Field Test | Provide staff and equipment meeting the requirements in the EMC Field Test Procedure. | Interface with NYCT to schedule and plan logistics and NYCT support for testing. Provide Hyundai Rotem staff familiar with the APS design and operation. | Assumes: * NYCT will witness the test. * No Hyundai Rotem internal test before the NYCT witness test. * Testing in NY can be performed within a one month duration for test equipment rental.
62 | APS | 3.19 | APS EMC Field Test Report | Develop the EMC Field Test Report. | Provide a submittal quality report of all test data.
63 | APS | 3.20 | All IEC types tests and routine tests in R160 Technical Specification Section 15.27 are required. | TBD | TBD | The necessary tests will be developed as part of the APS Requirements Allocation and Traceability Workshop.
64 | APS | 3.21 | English Copies of any standards being utilized in addition to those identified in the TS | Develop alternate standards narrative and comparison as required by R160 TS sections 1.6.19 and 1.6.20 | Provide English translations of any alternative standards used if an English language version cannot be purchased.
65 | APS | 3.22 | APS Cybersecurity Plan Compliance Review | Include Cybersecurity review in all Tenco APS Scope.
87 | APS | 3.23 | APS Compliance Auditing | Audit Hyundai Rotem's compliance tracking database. Spot check of 10% of the total compliance items tracked, selected at random. | Develop and maintain a compliance tracking database | Assumes that Hyundai Rotem has an established compliance tracking system.
66 | Commercial Risk Management | 4 | Commercial Risk Management
67 | Commercial Risk Management | 4.1 | Propulsion: Proposed list of deliverables with technical and commercial justification and defined expectations | Review Loan agreement and R211 TS to identify risks such as: * Ambiguities and internal conflicts * Hidden prerequisites to defined deliverables. * Deliverables that would be necessary for an actual procurement, but likely add little value to the Loan Agreement. * Deliverables incorporated by broadly cast references to other TS sections. * Deliverables incorporated by reference to outside specifications and standards. * Deliverables that have dependencies on the car builder, or other equipment that would be relevant within an actual procurement, but have no context within the scope of a Loan Agreement The resultant Tenco deliverable is a list of Hyundai Rotem Deliverables to provide to NYCT. |  | The Loan Agreement Section 2: "Cooperation Period" requires this effort to occur after the agreement is signed. "During such period {the cooperation period} each Party shall make its own determination as to the precise scope of information to be supplied and as to whether the services and equipment are appropriate for NYCT system/shop requirements." Tenco recommends that Hyundai Rotem work to mitigate the commercial risk of the Loan Agreement by identifying and planning for these uncertainty risks before entering into the Loan Agreement
68 | Commercial Risk Management | 4.2 | APS: Proposed list of deliverables with technical and commercial justification and defined expectations | Review Loan agreement and R160 TS to identify risks such as: * Ambiguities and internal conflicts * Hidden prerequisites to defined deliverables. * Deliverables that would be necessary for an actual procurement, but likely add little value to the Loan Agreement. * Deliverables incorporated by broadly cast references to other TS sections. * Deliverables incorporated by reference to outside specifications and standards. * Deliverables that have dependencies on the car builder, or other equipment that would be relevant within an actual procurement, but have no context within the scope of a Loan Agreement The resultant Tenco deliverable is a list of Hyundai Rotem Deliverables to provide to NYCT. |  | The Loan Agreement Section 2: "Cooperation Period" requires this effort to occur after the agreement is signed. "During such period {the cooperation period} each Party shall make its own determination as to the precise scope of information to be supplied and as to whether the services and equipment are appropriate for NYCT system/shop requirements." Tenco recommends that Hyundai Rotem work to mitigate the commercial risk of the Loan Agreement by identifying and planning for these uncertainty risks before entering into the Loan Agreement
69 | Commercial Risk Management | 4.3 | Propulsion Requirements Allocation and Traceability Workshop | Lead a structured TS Review workshop to help Hyundai Rotem's team identify and understand the R211 TS requirements that apply to the Loan Agreement Propulsion system and allocate them within the context of the Loan Agreement equipment design and deliverables. | Make the propulsion management, design, testing and manufacturing teams available for participation in the workshop. | Assumes : * HR has a requirements management toolkit and will populate it during the workshop. * The workshop will be held in person at the HR office near Seoul.
70 | Commercial Risk Management | 4.4 | APS Requirements Allocation and Traceability Workshop | Lead a structured TS Review workshop to help Hyundai Rotem's team identify and understand the R160 TS requirements that apply to the Loan Agreement APS system and allocate them within the context of the Loan Agreement equipment design and deliverables. | Make the APS management, design, testing and manufacturing teams available for participation in the workshop. | Assumes : * HR has a requirements management toolkit and will populate it during the workshop. * The workshop will be held in person at the HR office near Seoul.
71 | Commercial Risk Management | 4.5 | Propulsion Compliance program, per R211 TS 19.0 Materials and Workmanship | Included in Propulsion Requirements Allocation and Traceability Workshop |  | Subset of full requirements allocation and traceability
72 | Commercial Risk Management | 4.6 | APS Compliance program, per R160 TS Materials and Workmanship | Included in APS Requirements Allocation and Traceability Workshop |  | Subset of full requirements allocation and traceability
73 | Commercial Risk Management | 4.7 | APS Technical Cybersecurity | Expand the scope of the APS Requirements Allocation and Traceability Workshop to include the NYCT cybersecurity requirements.
74 | Commercial Risk Management | 4.8 | Propulsion Technical Cybersecurity | Expand the scope of the Propulsion Requirements Allocation and Traceability Workshop to include the NYCT cybersecurity requirements.
75 | Commercial Risk Management | 4.9 | Loan Agreement Project Cybersecurity
76 | Other Support | 5 | Other Support
77 | Other Support | 5.1 | Consultation regarding Kawasaki reference documents
78 | Other Support | 5.2 | Consultation regarding NYCT comments and direction
79 | Project Management | 6 | Project Management
80 | Project Management | 6.1 | General Project Management
81 | Project Management | 6.2 | Project Management Review of Propulsion | Tenco internal project management review of all propulsion deliverables
82 | Project Management | 6.3 | Executive Review of Propulsion | Tenco Executive Review of all propulsion deliverables.
83 | Project Management | 6.4 | Project Management Review of APS | Tenco internal project management review of all APS deliverables
84 | Project Management | 6.5 | Executive Review of APS | Tenco Executive Review of all APS deliverables.
85 | Project Management | 6.6 | Hyundai-Tenco weekly status meetings | Project manager and relevant SME participation in weekly status meeting