## High Level Task Matrix
LA Metro P2550 LRV Modernization RFP No. 2550-2019 Tenco EMC Task Matrix Time and Material Basis
P2550 LRV Modernization - EMC Task Matrix
Tenco requested scope: * Review of EMC documents from sub vendors * Creating technical documentations including CDRLs 02-04, 02-5, 02-13, 02-14, 02-18, and 02-19 * Attending technical meeting with the suppliers and Metro/LTK on demand * Creating EMI/EMC test procedures, analyzing the acquired data and making test reports * Performing EMI/EMC testing (including preparation of test instrument) and witness * Provide technical advice when KI faces EMI issues
Task Item | CDRL # | TS Section | Work Item | Tenco Scope | KI Scope | Supplier Scope | LA Metro Scope | Hours Rev. Nil | Hours Rev. A | Total Hrs Rev. Nil & A | Hours Rev. B | Total Hrs Rev. Nil,A,B | Misc. Cost Travel, Equip | Tech Spec Requirements | Assumptions
0] General Project Tasks
0.1 |  |  | Project EMC Technical Meetings | Attend technical meetings with KI and Metro/Hatch, as directed by KI | Coordinate, direct, and attend technical meetings, and invite Tenco as needed
0.2 |  |  | Technical Advice on Demand for EMC Issues | Provide KI with technical advice for EMI/EMC issues, as directed | Request technical advice from Tenco as needed.
1] Tenco EMC Scope for KI P2550
1.1] EMC Plan and Design
1.1.1 | 02-04 | 2.5.2.1-1 | EMC Program Plan (EMCP) Due at PDR | Draft EMCP per TS requirements. Revise EMCP per KI and LA Metro comments. | Review EMCP and provide comments. Submit to LA Metro. | Review and adhere to car-level EMCP. | Review, comment on, and accept EMCP. | [6 empty] | TS 2.5.2.1-1 requires that "The Contractor shall submit an EMC Program Plan to LACMTA for approval and implement an EMC program which fulfills all of LACMTA’s EMC requirements. a. Approval of the Contractor’s EMC Program Plan does not relieve the Contractor of the requirement to provide equipment that functions properly and with EMC in the LACMTA transit environment. b. The Contractor’s EMC Program Plan should contain details as required in this specification and should also have content as specified in APTA standard PR-E-S-010-98 (Standard for the Development of an Electromagnetic Compatibility Plan)."
1.1.2 | 02-05 | 2.5.2.2-1 | EMC Design Report (EDR) Due at PBDR | Request existing EMC design criteria from KI for EDR, including for APS and Propulsion. Draft EDR per TS requirements, including an Emissions Report section and a Susceptibility Report section. Provide EMC design criteria for all EMC sensitive items. Revise EDR per KI and LA Metro comments. | Provide Tenco with EMC design criteria. Review EDR and provide comments. Submit to LA Metro. | Provide supplier design information and EMC analysis for supplier scope. | Review, comment on, and accept EDR. | [6 empty] | TS 2.5.2.2-1 requires that "The Contractor’s EMC Program shall include an EMC Design Report documenting the EMC characteristics of the electrical and electronic portions of the LRV. a. The EMC Design Report shall consist of an Emissions Report section and a Susceptibility Report section. b. The Emissions Report section shall document the design provisions to achieve the specified emission limits including: i. Equipment layout, circuit routing, frequency coordination, filters, interconnections, grounding, and shielding; ii. EMC characteristics of the Propulsion and APS; iii. Conductive EMI Protection System (CEMIPS), if provided; and iv. The simulated combined emissions of the Propulsion and APS in a P2550 vehicle, and of a worst-case P2550 LRV consist in a worst-case LACMTA track circuit. c. The Susceptibility Report section shall document the design provisions to achieve suitable immunity of LRV equipment against EMI"
1.2] EMI Field Test
1.2.1 | 02-13 02-18 | 2.5.2.4-5.b 2.5.2.9-3 | EMI Field Test Procedure (EFTP) Train to Wayside EMI Test Procedure (TWETP) Due at PBDR | Request technical information from KI. Draft EFTP, consisting of: * Conducted Emissions Test Procedure * Inductive Emissions Test Procedure * Radiated Emissions Test Procedure * Cab Signal Interference Test Procedure * Train to Wayside EMI Test Procedure Revise EFTP per KI and LA Metro comments. | Provide requested info and EFTP from prior projects. Review EFTP and provide comments. Submit to LA Metro. | Provide guidance for equipment setup as needed. | Designate test track and provide description including mile marker location. Review, comment on, and accept EFTP. | [6 empty] | TS 2.5.2.4-5.b requires that "The Contractor shall submit an EMI Field Test Procedure for LACMTA approval, perform the test with a LACMTA witness, to LACMTA’s satisfaction, and submit an EMI Field Test Report for LACMTA approval." TS 2.5.2.9-3 requires that "The Contractor shall submit test procedures for approval, perform a field qualification test, and submit a test report for approval demonstrating that the LRV conforms to the TWC EMI criteria." 1. The Contractor shall determine and implement necessary design provisions to ensure that the TWC equipment (specified in TS 14) operates on all specified rail lines, TWC, and LRV modes and conditions. 2. The TWC equipment shall operate without disruption or degradation from EMI from any LRV source or track current, including from frequencies or harmonics of the Auxiliary Power Supply and Propulsion System. 3. [CDRL] The Contractor shall submit test procedures for approval, perform a field qualification test, and submit a test report for approval demonstrating that the LRV conforms to the TWC EMI criteria. 4. LACMTA may at its discretion require the Contractor to perform the test on a second randomly selected LRV or operating train consist | Assumption: Tenco will perform the testing at LA Metro test track, with participation from one or more KI test engineers. Assumption: Tenco will not perform or be present at lab or factory testing. Tenco can provide lab or factory testing or witnessing as additional scope. Assumption: Tenco will provide one comprehensive report to cover CDRLs 02-13 EFTP and 02-18 TWETP.
1.2.2 |  | 2.5.2.4-5.b | EMI Field Test | Perform tests: * Conducted Emissions Test * Inductive Emissions Test * Radiated Emissions Test * Cab Signal Interference Test * Train to Wayside EMI Test | Perform guidance and coordination for EMC tests: * LRV * Test engineer to operate train and answer questions * Equipment supplier technical staff to answer questions and attend tests * All coordination with LA Metro * Shared test equipment such as chart recorder | Provide technical staff for tests. | Provide LA Metro staff and facilities to enable efficient EMC tests: * Access to track, yard, shop, mainline, LRVs, and Metro facilities * Test operators and maintenance staff as needed to perform tests * Clearance from ROC * Track coordination meeting authorization * Communications * Security Designate test track and provide description including mile marker location. | [6 empty] | TS 2.5.2.4-5.b requires that "The Contractor shall submit an EMI Field Test Procedure for LACMTA approval, perform the test with a LACMTA witness, to LACMTA’s satisfaction, and submit an EMI Field Test Report for LACMTA approval." TS 2.5.2.9-3 requires that "The Contractor shall submit test procedures for approval, perform a field qualification test, and submit a test report for approval demonstrating that the LRV conforms to the TWC EMI criteria. | Assumption: Tenco will perform the testing at an LA Metro test track, with participation of KI test engineers and managers. Assumption: Tenco and KI will complete the field testing in one test session of two prep days, eight test days
1.2.3 | 02-14 02-19 | 2.5.2.4-5.b 2.5.2.9-3 | EMI Field Test Report (EFTR) Train to Wayside EMI Test Report (TWETR) Due at FDR | Draft car-level EFTR., consisting of: * Conducted Emissions Test Report * Inductive Emissions Test Report * Radiated Emissions Test Report * Cab Signal Interference Test Report. * Train to Wayside EMI Test Report. If LRV does not pass tests, assist KI in developing and drafting recommended mitigations. Work with KI to get LA Metro approval. Revise car-level EFTR per KI and LA Metro comments. | Review EFTR and provide comments. Submit to LA Metro.A | Review EFTR. | Review, comment on, and accept EFTR. | [6 empty] | TS 2.5.2.4-5.b requires that "The Contractor shall submit an EMI Field Test Procedure for LACMTA approval, perform the test with a LACMTA witness, to LACMTA’s satisfaction, and submit an EMI Field Test Report for LACMTA approval." TS 2.5.2.9-3 requires that "The Contractor shall submit test procedures for approval, perform a field qualification test, and submit a test report for approval demonstrating that the LRV conforms to the TWC EMI criteria.
2] Possible Tenco Scope
1.3] EMI Safety Analysis
1.3.1 | N/A | 2.5.2.11-6 | EMI Safety Analysis (ESA) Note: Not a TS required CDRL. However, CEMIPS assessment is specified to be in ESA. Suggested: Provide at PBDR, FDR | Draft Car-Level ESA, providing assessment of EMI hazards and mitigations. Request required content from KI and system suppliers including Propulsion, APS, and Onboard ATC. Update Car-Level ESA per KI and LA Metro comments. Make car level CE model, allocate limits, calculate lab limits. | Review Car-Level ESA and provide comments. Submit to LA Metro. Promptly provide all needed tech info for ESA. | Promptly provide all needed supplier content for ESA. Accept and apply CE limits | Review, comment on, and approve Car-Level ESA. | [6 empty] | TS 2.5.2.11-6 requires that "The Contractor shall provide CEMIPS safety and reliability analyses for approval. The CEMIPS shall be designed with an equipment safety and integrity level as required in the EMI Safety Analysis. If the EMI Detector prevents the HSCB from closing, then this shall be indicated to the MDS. A bypass switch shall permit closure of the HSCB and its action shall also impose a vehicle speed limit." | Note: TS 2.5.2.11-6 mentions an EMI Safety Analysis, but the TS does not explicitly require an ESA as a CDRL. Assumption: Tenco writes the car-level ESA,. Tenco states ESA requirements for system suppliers. Note: Since EMC depends mostly on Propulsion and APS, Tenco recommends that KI/Tenco prepare a car-level ESA covering train, railcar, Propulsion, APS, and ATC EMI hazards.
2] Lab Test EMC Scope for P2550
2.1] Equipment-Level EMC Test - Not in Tenco Estimate
2.1 | 02-07 02-11 | 2.5.2.4-2 2.5.2.4-4.b | APS EMC Test Procedure (APS ETP) Due at PBDR |  | Review APS ETP Rev 0 for conducted and inductive emissions. Ensure adequate APS Lab Test for conducted and inductive emissions. As required, if not covered by previous supplier certification, review APS ETP for EN50121-3-2 tests. Review APS ETP Rev 1 and provide APS supplier with comments. Submit to LA Metro. | APS supplier provide detailed Propulsion ETP and update per KI and Metro comments. | Review, comment on, and accept APS ETP. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." TS 2.5.2.4-4.b requires that "The Contractor shall submit an APS EMC Test Procedure for LACMTA approval, perform the test with a LACMTA witness to LACMTA’s satisfaction, and submit an APS EMC Test Report for LACMTA approval."
2.2 | 02-08 02-12 | 2.5.2.4-2 2.5.2.4-4.b | APS EMC Test Report (APS ETR) Due at FDR |  | Attend APS Lab Test and provide technical guidance to ensure satisfactory for conducted and inductive test and results. Review APS ETR Rev 0 and provide APS Supplier with comments. Review APS ETR Rev 1 and provide KI with comments. Submit to LA Metro. | APS supplier plan, perform, and report on Propulsion Lab Tests. | Review, comment on, and accept APS ETP. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." TS 2.5.2.4-4.b requires that "The Contractor shall submit an APS EMC Test Procedure for LACMTA approval, perform the test with a LACMTA witness to LACMTA’s satisfaction, and submit an APS EMC Test Report for LACMTA approval." | Assumption: Tenco budget for Lab Test attendance and guidance for conducted and inductive tests is 5 work days for 1 engineer. Assumption: APS equipment suppliers will perform tests as needed per EN 50121-3-2, and provide certified test reports, without Tenco attendance.
2.3 | 02-07 02-09 | 2.5.2.4-2 2.5.2.4-3.b | Propulsion Lab EMC Test Procedure (Propulsion ETP) Due at PBDR |  | Review Propulsion ETP Rev 0 for conducted and inductive emissions. Ensure adequate Propulsion Lab Test for conducted and inductive emissions. As required, if not covered by previous supplier certification, review Propulsion ETP for EN50121-3-2 tests. Review Propulsion ETP Rev 1 and provide Propulsion supplier with comments. Submit to LA Metro. | Propulsion supplier provide detailed Propulsion ETP and update per KI and Metro comments. | Review, comment on, and accept Propulsion ETP. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." TS 2.5.2.4-3.b requires that "The Contractor shall submit a Propulsion Lab EMC Test Procedure for LACMTA approval, perform the test with a LACMTA witness to LACMTA’s satisfaction, and submit a Propulsion Lab EMC Test Report for LACMTA approval."
2.4 | 02-08 02-10 | 2.5.2.4-2 2.5.2.4-3 2.5.2.4-3.b | Propulsion Lab EMC Test Report (Propulsion ETR) FDR |  | Attend Propulsion Lab Test and provide technical guidance to ensure satisfactory for conducted and inductive test and results. Review Propulsion ETR Rev 0 and provide KI with comments. Review Propulsion ETR Rev 1 and provide Propulsion supplier with comments. Submit to LA Metro. | Propulsion supplier plan, perform, and report on Propulsion Lab Tests. | Review, comment on, and accept Propulsion ETP. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." TS 2.5.2.4-3 requires that "The Contractor shall conduct a laboratory test on a complete set of Propulsion equipment, to confirm that electromagnetic emissions meet CE, Inductive Emission and Cab Signal Interference limits for a representative propulsion system when measured in a lab environment. a. The Contractor shall calculate ‘lab’ EMI limits as part of the EMI Design Report." TS 2.5.2.4-3.b requires that "The Contractor shall submit a Propulsion Lab EMC Test Procedure for LACMTA approval, perform the test with a LACMTA witness to LACMTA’s satisfaction, and submit a Propulsion Lab EMC Test Report for LACMTA approval." | Assumption: Tenco budget for Lab Test attendance and guidance for conducted and inductive tests is 5 work days for 1 engineer. Assumption: Propulsion equipment suppliers will perform tests as needed per EN 50121-3-2, and provide certified test reports, without Tenco attendance.
2.5 | 02-07 | 2.5.2.4-2 | Equipment-Level EMC Test Procedures (ELETP) per EN50121-3-2 Due at PBDR [For equipment other than propulsion and APS] |  | As required, if not covered by previous supplier certification, review APS ETP for EN50121-3-2 tests, review EMC-dependent ELETP Rev 0s and provide KI with comments. Review Onboard ATC Cab Signal Interference ELETP and provide comments Review Equipment ELETP Rev 1s and provide suppliers with comments. Submit to LA Metro. | Provide ELETP test procedures for supplier scope as required. | Review, comment on, and accept ELETPs. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." | Assumption: Most equipment suppliers will provide test reports compliant with EN 50121-3-2; and therefore not require procedures, review, or new test reports. Assumption: Tenco budget covers review of four test procedures, for suppliers providing new or modified equipment requiring a new EN50121-302 test and report.
2.6 | 02-08 | 2.5.1.4-2 | Equipment Level EMC Test Reports per EN50121-3-2 Due at FDR [For equipment other than propulsion and APS] |  | As required, if not covered by previous supplier certification, review APS ETP for EN50121-3-2 tests, review EMC-dependent ELETR Rev 0s and provide suppliers with comments. As required, review previous EN50121-3-2 test reports and certificates to determine suitability of past certificate for P2550 procurement. Attend and provide guidance for Onboard ATC Cab Signal Interference Test. Review Onboard ATC Cab Signal Interference ELETR and provide comments Review EMC-dependent ELETP Rev 1s and provide suppliers with comments. Submit to LA Metro. | Provide Equipment Level EMC test reports for supplier scope as required. | Review, comment on, and accept ELETRs. | [6 empty] | TS 2.5.2.4-2 requires that "The Contractor shall submit Equipment-level EMC Test Procedures for approval, perform tests, and submit Equipment-level EMC Test Reports for approval demonstrating that Vehicle subsystems conform with EN 50121-3-2, “Railway Applications-Electromagnetic: Rolling Stock-Apparatus”, emission and immunity limits." TS 2.5.2.4-1 states that "Certified results of prior tests of identical equipment may be submitted for approval." | Assumption: Most equipment suppliers will provide test reports compliant with EN 50121-3-2; and therefore not require procedures, review, or new test reports. Assumption: Tenco budget covers review of four test reports, for suppliers providing new or modified equipment requiring a new EN50121-302 test and report.
Note on I27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 70 * 2 = 140
Note on J27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 30 * 2 = 60
Note on L27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15 * 2 = 30
Note on I28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10 * 6 = 66
Note on J28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 * 6 = 18
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 * 6 = 18

## TCMS Interfaces (hidden)
Systems that must interface with TCMS
| TS 17.2-2.a | The following vehicle systems shall provide a wired network interface to the Monitoring and Diagnostic System (MDS):
1 | TS 17.2-2.a.i | Automatic Train Protection (ATP) System
2 | TS 17.2-2.a.ii | Auxiliary Power System (APS)
3 | TS 17.2-2.a.iii | Communication Control Unit (CCU)
4 | TS 17.2-2.a.iv | Door Control Unit (DCU)
5 | TS 17.2-2.a.v | Electromagnetic Interference Detector, (if used)
6 | TS 17.2-2.a.vi | Electronic Brake Control Unit (ECU)
7 | TS 17.2-2.a.vii | Event Recorder (ER)
8 | TS 17.2-2.a.viii | Heating, Ventilation, and Cooling (HVAC) System
9 | TS 17.2-2.a.ix | Low Voltage Power Supply (LVPS)
10 | TS 17.2-2.a.x | Traction Control Unit (TCU)
11 | TS 17.2-2.a.xi | Train to Wayside Communication (TWC) System
| TS 17.2-2.c | The Contractor shall submit an Interface Control Document (ICD) for each networked controller.
| TS 17.4.3-3 | MDS must also interface to the MVB

## Assumptions (hidden)
Assumptions
1 | The total hours for each task includes drafting Rev.NIL and two revisions (Rev.A and Rev.B) responding to Talgo & Metro comments.
2 | Woojin and Talgo promptly provide documents upon Tenco request.
3 | Tenco will not interface with Talgo's suppliers.
4 | Woojin and Talgo are responsible to obtain all Supplier Documents needed to support system integration.
5 | Estimate is Time and Materials.
6 | Tenco will stop work when the funds authorized by P.O. are exhausted.
7 | Estimated total does not include contingency.
8 | Tenco recommends that Woojin reserve a 20% contingency.
9 | Documents are produced at the right time in the project; not too early, not too late. * If docs required too soon: Necessary information is not available, forces later revisions. Increased cost. * If docs required too late: Rush job, requires higher rate labor. Increased cost.
10
11
12
13
14
15
16
17
18
19
20

## Acronyms (hidden)
APC | Automatic Passenger Counting System
PBDR | Production Based Design Review
PDR | Preliminary Design Review
SI | System Integration

## NYCT 8th Av - Tenco Task Matrix (hidden)
NYCT 8th Avenue CBTC S-48006 Contract Tenco Proposed Scope for CBTC EMC Program
Turner Engineering Corporation (Tenco), April 30, 2019 Terms: Tenco proposes to perform the work on a time and material rate, at our engineering service rates in effect at the time. We recommend this arrangement, since a fixed price must include a risk budget which will be significant for a NYCT CBTC project.
CBTC EMC Program Task Matrix
Task Item | CDRL # | TS Section | Work Item | Tenco Scope | CRSC Scope [Prime Contractor] | External Supplier Scope | NYCT Scope | Comments
0] EMC Project Management
0.1 |  |  | Project Management | Manage project. Provide EMC single point of contact, as directed by CRSC. Coordinate with CRSC and produce monthly Progress Reports. Attend meetings per CRSC requests. | Provide EMC program direction. Respond to Tenco and external supplier requests. | Provide documentation requested by Tenco and CRSC. | None
1] EMC Program
1.1.1 |  | 24F 3.5; 1N 2.7 | EMC Control Plan (EMCP) | 1] Develop EMC Control Plan (EMCP) that covers all project EMC requirements, actions, and deliverables. EMCP Appendices will include other specified EMC deliverables listed below: EMOP per 1N 2.5, DIP per 1N 2.6, EMC Test Plan per 24F 1.5g, and Qualifications per 1N 2.11. 2] Submit EMCP to CRSC and NYCT. Revise per review comments. 3] Update EMCP whenever there are major changes to any part of the design that relates to EMI/EMC. | Provide requested documentation to Tenco to create EMCP. Provide CBTC system expertise with Tenco via teleconference and email communications. Review and comment on EMCP, including appendices in Task Items 1.1.2 to 1.1.5. Submit EMCP to NYCT. Provide NYCT comments on EMCP to Tenco. Respond to Tenco and relay documents between Tenco and NYCT. | Provide requested documentation to Tenco to create EMCP. Provide supplier expertise with Tenco via teleconference and email communications. Accept and implement EMCP. | Review and comment on EMCP. Approve EMCP.
1.1.2 |  | 1N 2.5 | EMI/EMC Management and Organizational Plan (EMOP) Provided as EMCP Appendix A. | Develop EMI/EMC Management and Organizational Plan (EMOP). Provided as an EMCP Appendix, rather than a separate deliverable, if acceptable to NYCT and CRSC. | Provide requested documents and information to Tenco. Direct document flow between Tenco and NYCT. Review and comment on EMOP. Submit EMOP to NYCT. Provide NYCT comments on EMOP to Tenco. Accept and implement EMOP. | Provide requested documents and information to Tenco, if necessary. Review and comment on EMOP. Accept and implement EMOP. | Review and approve EMI/EMC Management and Organizational Plan.
1.1.3 |  | 1N 2.6 | Design Implementation Plan (DIP) Provided as EMCP Appendix B. | As an appendix of the EMCP, develop a detailed Design Implementation Plan (DIP). Review, approve, and sign DIP submittals for equipment, installation and layout prior to submitting to the NYCT. Assist CRSC with Monthly EMI/EMC Design and Implementation Report by drafting progress report. Provided as an EMCP Appendix, rather than a separate deliverable, if acceptable to NYCT and CRSC. | Review and comment. Respond to Tenco and request and direct document flow between Tenco and NYCT. Submit DIP to NYCT. Provide NYCT comments on DIP to Tenco. Provide draft monthly EMI/EMC Design and Implementation Report to supplier scope activities. Submit Monthly EMI/EMC Design and Implementation Report, within ten days of the end of the month. | Provide requested documents and information to Tenco, if necessary. Accept and implement DIP. | Review and approve Design Implementation Plan.
1.1.4 |  | 24F 1.5g | EMC Test Plan Provided as EMCP Appendix C. | Draft EMC Test Plans and coordinate with CRSC for CBTC equipment submittal and EMC waivers. Provided as an EMCP Appendix, rather than a separate deliverable, if acceptable to NYCT and CRSC. | Before EMC Test Plans are submitted for NYCT review, provide requested documentation and information to Tenco. Review and comment. Submit EMC Test Plan to NYCT. Provide NYCT comments on EMC Test Plan to Tenco. Direct document flow between Tenco and NYCT. Submit waiver requests to NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and comment on EMCP. Approve EMC Test Plan. Review and approve CBTC waiver requests.
1.1.5 |  | 1N 2.11 | EMC Qualifications Provided as EMCP Appendix D. | Within 60 days after the notice of award of the contract, Submit ten professionally bound copies of the resumes and qualifications per TS 1N 2.11. Provided as an EMCP Appendix, rather than a separate deliverable, if acceptable to NYCT and CRSC. | Provide requested documents and information to Tenco. Review and comment. Respond to Tenco requests. Direct document flow between Tenco and NYCT. Submit EMC Quals to NYCT. Provide NYCT comments on EMC Quals to Tenco. | Provide requested documents and information to Tenco, if necessary. | Approve Qualifications documents.
1.2 |  | 1N 2.11 | Submittal Requirements | Provide electronic copies of all plans, procedures, and reports to CRSC for work performed by Tenco. Review and then provide electronic copies of all plans, procedures, and reports to CRSC for work performed by CRSC. Provide certificates of calibration for test equipment for tests performed by Tenco. | For all plans, procedures, certificates of calibration, and reports, submit ten professionally bound copies to NYCT, with hard covers, indexed, and include a table of contents, executive summary, write-ups, tables, graphs, photographs, technical appendix and supporting documentation, as directed by the Engineer. Provide electronic copies of all plans, procedures, and reports to Tenco for work performed by CRSC contracted test labs. | Provide requested documents and information to Tenco, if necessary.
1.3 |  | 24F 3.7 | EMC Design Report (EDR) | Manage EMC Design Report (EDR) of the CBTC equipment. The EDR will include Field Installation Verification Forms. Provide EDR to CRSC for review and submittal to NYCT. Revise per review comments. | Provide requested information to Tenco, such as Draft EMC Design Reports, design plans and documentation. Submit EDR to NYCT. Direct document flow between Tenco and NYCT. Respond to NYCT comments on EDR. | Provide requested documents and information to Tenco, if necessary. | Review and approve any standard manufacturer models that are modified to comply with EMI/EMC requirements. Review and comment on EDR. Approve EDR.
1.4 |  | 24F 3.9 | EMC Signaling Compatibility Analysis (ESCA) | Perform EMC Signaling Compatibility Analysis (ESCA) for all operating frequencies from DC to 10 GHz. Update ESCA as required per comments from CRSC and NYCT. | Provide ESCA information and documentation as requested by Tenco. Review and comment on ESCA. Submit ESCA to NYCT. for approval after all field and laboratory EMI/EMC testing has been completed. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and comment on ESCA. | This proposal assumes that the track circuit design entirely fulfills the criterion 1N 2.8.o.4: "Track circuit testing is not required for track circuits that utilize pre-approved track relays and matching transformers." The ESCA will check all in-scope track circuit final design plans, and will report the results. If the results show that all track circuits are a better case than the NYCT worst-case track circuits, the ESCA will conclude that no track circuit tests are required per 1N 2.8.o. If the design includes track circuits that do not comprise a better case than the NYCT worst-case track circuit, analysis, test procedure, test, and report work will be an added scope and cost task.
2] Certification Test
1.5 |  | 1N 2.8.a.3 | EMC Factory Test | Draft EMC Factory Test Procedure Guidelines for EMC Tests. Check that CRSC selected suitable Qualified Test Lab. Review and comment on Test Procedures provided by contracted CRSC Test Lab. Monitor tests. Resolve questions about test procedures. Review CRSC EMC Factory Test Reports and provide comments. | Use EMC Factory Test Procedure Guidelines to guide Qualified Test Lab Test Procedures. Get compliant Test Procedures. After review by Tenco, update as needed. Submit Test Procedures to NYCT. Notify NYCT in writing the dates of the test at least 60 days prior to the start of testing. Perform EMC Factory Tests at approved Test Lab. Submit Tenco-reviewed EMC Factory Test Report to NYCT. Revise per review comments. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and Approve EMC Factory Test Procedures. Approve date and location for Factory Test and Witness if necessary. Review and Approve EMC Factory Test Report.
1.5.1 |  | 1N 2.8.a.3 | EMC Factory Test Procedure | Draft EMC Factory Test Procedure Guidelines for: * Conducted and Radiated Emissions Tests * Susceptibility tests to determine the susceptibility of equipment to external electromagnetic emissions * Electrostatic Discharge Tests to determine the susceptibility of equipment to external electromagnetic electrostatic emissions * Radio Susceptibility Qualification Tests. Guidelines will be used by CBTC Supplier contracted test labs to provide required test procedures. Submit test procedure guidelines to CBTC Supplier. Check that CBTC Supplier selected suitable Qualified Test Lab. Review and comment on Test Procedures provided by contracted CBTC Supplier Test Lab. |  |  | Review and Approve EMC Factory Test Procedures. | "The following equipment shall be required to undergo EMI/EMC testing as specified in latest edition of MIL-STD-461 and as specified herein: • Equipment Containing Microprocessors • Code Cabinets and associated Equipment • Digital Meters • Internal Microprocessor Equipment for Interlocking and Maintainer Panels • LED Signals • Microprocessor based power transfer switches • Electronic ballasts" - TS.1N.2.3.a "h. All equipment shall be certified for compliance with Federal Communications Commission (FCC) Rules, including Part 15." - TS.1N.2.3.h
1.5.2 |  | 1N 2.8.a.3 | EMC Factory Test | Monitor tests. Resolve questions about test procedures. As an added scope item, provide skilled EMC design engineers to attend tests and/or provide on-call technical expertise to resolve problems if any arise during Factory EMC Tests. |  |  | Approve date and location for Factory test. Witness EMC Factory Test, as necessary. | "3.8 EMC Test Requirements a. All EMC testing shall be performed on a production level sample of the equipment. The equipment shall be functioning during the testing as it will be in actual service. The equipment shall be arranged for testing as it will be arranged in the field in actual service. The detailed test procedures shall include diagrams showing the exact configuration for each piece of equipment. The test procedures shall also outline specific mode of operation for the equipment under tests as well as the failure criteria. b. Where any EMI levels are observed during the EMC Site Surveys that exceed the levels described in the sections below, the levels observed during the Environmental test shall apply. c. When carborne CBTC equipment is required by the Contract, carborne equipment shall comply with the requirements of EN 50121-3-2. d. Wayside communications equipment shall comply with the requirements of EN 50121-4." - TS.24F.3.8
1.5.3 |  | 1N 2.8.a.3 | EMC Factory Test Report | Review CBTC Supplier Contractor EMC Factory Test Reports and provide comments. |  |  | Review and Approve EMC Factory Test Report.
1.6 |  | 1N 2.8.o | Track Circuit Test | The proposal assumes that the design does not include any track circuits that are worse than the NYCT worst-case track circuit, and that therefore, no test procedures or tests are required. This will be shown in the ESCA. If the design includes track circuits that are not better than the NYCT worst-case track circuit: Develop Track Circuit Test Procedures, Plan and Perform the Track Circuit Test, and Write and Submit Track Circuit Test Report. Submit procedure and report to CRSC. Revise per review comments. | If the design includes track circuits that are not better than the NYCT worst-case track circuit: Provide complete design information for all revised or new track circuits. Review and provide feedback on Track Circuit Test Procedures. Submit Track Circuit Test Procedures to NYCT. Attend Track Circuit Test. Review and provide feedback on Track Circuit Test Report. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and Approve Track Circuit Test Procedures. Approve test date and location. For tests at NYCT, schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. Witness Track Circuit Test, as necessary. Review and Approve Track Circuit Test Report. | As noted in the ESCA, this proposal assumes that the track circuit design entirely fulfills the criterion 1N 2.8.o.4: "Track circuit testing is not required for track circuits that utilize pre-approved track relays and matching transformers." The ESCA will check all in-scope track circuit final design plans, and will report the results. If the results show that all track circuits are a better case than the NYCT worst-case track circuits, the ESCA will conclude that no track circuit tests are required per 1N 2.8.o. If the design includes track circuits that do not comprise a better case than the NYCT worst-case track circuit, analysis, test procedure, test, and report work will be an added scope and cost task.
1.6.1 |  | 1N 2.8.o | Track Circuit Test Procedures | The proposal assumes that the design does not include any track circuits that are worse than the NYCT worst-case track circuit, and that therefore, no test procedures or tests are required. This will be shown in the ESCA. If the design includes track circuits that are not better than the NYCT worst-case track circuit: * Develop detailed Track Circuit Test Procedures that investigate and document the susceptibility characteristics of any new or modified track circuits furnished and installed. Determine the threshold amplitude and frequency of spurious continuous wave and impulse type signals that cause malfunction of track circuits. Demonstrate to the Engineer, by means of laboratory and wayside tests, that the track circuits do not malfunction in the presence of high-level train generated electromagnetic signals. * Track Circuit Test Procedures will detail tests for worse case track circuit configuration as defined in "NTT EMC Standards For Procurement of New Technology Trains", Revision 1.1, January 31, 1996 and "NTT Conducted EMI Test Procedure," Revision 1.2 prepared by Turner, Gold, France, Engineering. * Submit Track Circuit Test Procedure to CBTC Supplier and NYCT. Revise per review comments. |  |  | Review and Approve Track Circuit Test Procedures. | As noted in the ESCA, this proposal assumes that the track circuit design entirely fulfills the criterion 1N 2.8.o.4: "Track circuit testing is not required for track circuits that utilize pre-approved track relays and matching transformers." The ESCA will check all in-scope track circuit final design plans, and will report the results. If the results show that all track circuits are a better case than the NYCT worst-case track circuits, the ESCA will conclude that no track circuit tests are required per 1N 2.8.o. If the design includes track circuits that do not comprise a better case than the NYCT worst-case track circuit, analysis, test procedure, test, and report work will be an added scope and cost task.
1.6.2 |  | 1N 2.8.o | Track Circuit Test | If the design includes track circuits that are not better than the NYCT worst-case track circuit: * Plan the test. * Provide a 3-man test crew onsite for required test duration to make measurements at Tenco lab or at designated NYCT site. * Perform Track Circuit test at approved locations. |  |  | Approve test date and location. For tests at NYCT, schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. Witness Track Circuit Test, as necessary. | See above comment.
1.6.3 |  | 1N 2.8.o | Track Circuit Test Report | If the design includes track circuits that are not better than the NYCT worst-case track circuit: * Write Track Circuit Test Report. Per TS 24F 1.5I, include test personnel, test schedule, and test equipment information. * Submit report to CBTC Supplier and NYCT for review. Revise per review comments. |  |  | Review and Approve Track Circuit Test Report. | See above comment.
3] Field Tests
1.7 |  | 24F 3.6 1N 2.8 | EMC Site Survey | Develop EMC Site Survey Test Procedure (ESSP) to determine the NYCT EMI/EMC environment for the CBTC system. Submit procedure to CRSC and NYCT for review. Revise per review comments. Plan and perform the EMC Site Survey. Write EMC Site Survey Report (ESSR) that emphasizes operating frequencies which correspond to CBTC equipment and other critical frequencies documented in the EMC Design Report. Submit ESSR to CRSC and NYCT. Revise per review comments, as necessary. | Respond to Tenco Requests. Review and provide feedback on ESSP. Submit ESSP to NYCT. Attend EMC Site Survey. Provide Point of Contact for Tenco and NYCT coordination. Review and provide feedback on ESSR. Submit ESSR to NYCT. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | NYCT Engineer approve Test Procedures. Approve test dates and location. Schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. Provide Witness for EMC Site Survey Test. Review and provide feedback on ESSR. Engineer approve Test Report at PDR.
1.7.1 |  | 24F 3.6 1N 2.8 | EMC Site Survey Procedure (ESSP) | Develop EMC Site Survey Test Procedure (ESSP) to determine the NYCT EMI/EMC environment for the CBTC system. The EMC Site Surveys will cover enough field locations such that the worst-case limits can be determined. Develop tests to determine the emission levels and susceptibility levels of NYCT equipment which could interact with the CBTC system. Submit procedure to CBTC Supplier and NYCT for review. Revise per review comments. |  | Provide requested documents and information to Tenco, if necessary. | Review and provide feedback on ESSP. NYCT Engineer approve Test Procedures. | "Pre-printed survey and measurement forms shall be developed and included in each section of the EMI/EMC Compliance Program. The forms shall include spaces for: readings, room designation, station name, engineering stationing, track number, peak or off-peak time, signatures of tester and persons witnessing testing, serial number of equipment used and all other pertinent information, as directed by the Engineer. The completed forms shall be submitted ten days after the tests are completed." - TS 1N.2.11.e "A complete description and catalog cuts for all test equipment, meters, chart recorders, laboratory testing equipment and all other instrumentation used for the field surveys, measurement testing and laboratory tests, shall be submitted as part of the overall EMI/EMC Compliance Program. All current certificates of calibration shall also be included in the submittal." - TS 1N.2.11.g Note: TS 1N.2.11.g requires information such catalog cuts for test equipment, meters, chart recorders and other lab and field testing equipment. Tenco will not know most of this information before performing EMI tests, but it will be included in Report appendices.
1.7.2 |  | 24F 3.6 | EMC Site Survey | Plan the Site Survey Attend NYCT Safety Training, as required. Provide a 3-man test crew onsite for required test duration to make measurements at designated NYCT site. Perform EMC Site Survey Test. |  | Provide requested documents and information to Tenco, if necessary. | Approve test dates and location. Schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. Provide Witness for EMC Site Survey Test.
1.7.3 |  | 24F 3.6 | EMC Site Survey Report | Write EMC Site Survey Report (ESSR) that emphasizes operating frequencies which correspond to CBTC equipment and other critical frequencies documented in the EMC Design Report. Submit ESSR to Five Star Electric and NYCT. Revise per review comments, as necessary. |  |  | Review and provide feedback on ESSR. Engineer approve Test Report at PDR. | 3.8 EMC Test Requirements b. Where any EMI levels are observed during the EMC Site Surveys that exceed the levels described in the sections below, the levels observed during the Environmental test shall apply."
1.8 |  | 24F 3.10 1N 2.8.q | Final Field EMC Test | Draft Final Field EMC Test Procedure to test compliance of the CBTC system to the requirements. Revise per review comments. Plan the Field EMC Test. After all installation work is complete, perform required Final Field EMC Tests. Coordinate with NYCT for access to, control of, and safe operation of NYCT staff, track, trains, equipment, and facilities. Analyze results of Final EMC Test, prepare compliance matrix to record results of individual systems, and draft Final EMC Test Report. Submit to CRSC and NYCT. Revise per review comments. If recommended mitigations are not approved by NYCT, work with CRSC to submit modified design for approval, with test results which show the design meets the requirements. | Review and provide feedback on EMC Test Procedure. Submit to NYCT. Coordinate with NYCT for access to, control of, and safe operation of NYCT staff, track, trains, equipment, and facilities. Attend Field EMC Test. After Final Field EMC tests are completed and approved by the Engineer, request a "Bulletin" for taking equipment into service. If recommended mitigations are not approved by NYCT, submit modified design for approval, with test results which show the design meets the requirements. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and provide feedback on ESTR. Approve EMC Test Procedure. Approve test dates and locations. Provide Witness for EMC Field Test. Approve the Contractor's Final Field EMC Test Reports and equipment, once CBTC Supplier has demonstrated satisfactory CBTC operation in worst case operating modes with approved margins.
1.8.1 |  | 24F 3.10 1N 2.8.q | Final Field EMC Test Procedure | Draft Final Field EMC Test Procedure to test compliance of the CBTC system to the requirements of EN 50121, and section 3.4 of the MTA/NYCT AC Train EMC Standard. Prepare Test Plans that quantitatively demonstrate that the item achieves the margin identified in the EMC Design Report worst case conditions. The Final Field EMC Test Procedure will include the following sections: Introduction, Schedule, Equipment Configuration Under Test, Test Track, Test Equipment Configuration and Calibration, Test Runs, Test Methods, Test Data Collection Procedures, and Test Report Format. Submit EMC Test Plan to Five Star Electric, and NYCT. Revise per review comments. Provide draft EMC report to CRSC. Revise per review comments as necessary. |  | Provide requested documents and information to Tenco, if necessary. | Review and provide feedback on ESTR. Approve EMC Test Procedure. Schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. | Procedures will follow the guidelines of FCC OET Bulletin 65 regarding human exposure to radiofrequency electromagnetic fields.
1.8.2 |  | 24F 3.10 1N 2.8.q | Final Field EMC Test | Plan the Field EMC Test. After all installation work is complete, perform required Final Field EMC Tests per the EN 50121 series of standards, section 3.4 of the MTA/NYCT AC Train EMC Standard and section 1N 2.8. Coordinate with NYCT for access to, control of, and safe operation of NYCT staff, track, trains, equipment, and facilities. |  | Provide requested documents and information to Tenco, if necessary. | Approve test dates and locations. Schedule and provide NYCT facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; signal operations to connect to rails if needed; safety and flagging; logistics and coordination. Provide Witness for EMC Field Test.
1.8.3 |  | 24F 3.10 1N 2.8.q | Final Field EMC Test Report | Analyze the results of each Final Field EMC test and determine if the equipment as built is suitable for deployment in the NYCT environment. Prepare a compliance matrix to record test results from individual equipment/systems in the presence of other equipment/systems. Write report that demonstrates EMC between all subsystems and equipment (both vital and non-vital) during all modes of operation while the subsystems and equipment are individually or collectively operated. Include Introduction, Schedule, Equipment Configuration Under Test, Test Track, Test Equipment Configuration and Calibration, Test Runs, Test Methods, Test Data Collection Procedures. Submit necessary EMC mitigations, as necessary. Provide draft EMC report to CBTC Supplier. Revise per review comments as necessary. If recommended mitigations are not approved by NYCT, work with CBTC Supplier to submit modified design for approval, with test results which show the design meets the requirements. |  |  | Approve the Contractor's Final Field EMC Test Reports and equipment, once CBTC Supplier has demonstrated satisfactory CBTC operation in worst case operating modes with approved margins.
1.9 |  | 24F 3.11 | EMC Safety Analysis (ESA) | Draft EMC Safety Analysis (ESA) report. Provide draft ESA to CRSC. Revise per review comments as necessary. | Respond to Tenco Requests. Provide all required technical information for ESA to Tenco. Review and provide feedback on ESA. Submit to NYCT. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and provide feedback on ESA. Approve ESA.
1.10.1 |  | 1N 2.9 | EMI/EMC Training Course | Develop a course on EMI/EMC control, design and the EMI/EMC requirements. Provide personnel for EMI/EMC Training Course. Deliver Training Course. | Provide CBTC scope material for Training Course, as required. Respond to Tenco requests. Provide staff to attend training course. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Provide list of up to 35 NYCT staff to attend Training Course. Provide facilities to hold Training Course for NYCT staff. Approve attendance list, location and dates of the course. | Prime Contractor should request NYCT to clarify: * "Training Course will cover Testing and Certification of Wireless Devices given by National Technical Systems." This statement does not appear relevant to CBTC or rail EMC. Request to delete it. * Is timing of 120 days necessary?
1.10.2 |  | 1N 2.10 | EMI/EMC Training Video | Prepare a thirty minute video DVD on EMI/EMC fundamentals. Submit video to NYCT for approval. | Provide documentation requested by Tenco. Submit Training Video to NYCT. Direct document flow between Tenco and NYCT. | Provide requested documents and information to Tenco, if necessary. | Review and approve Training Video.
|  | 17A, 17JA, 17JB, 17JC, JC-A, 17JL, 17JM, 17K, 17M | EMC requirements in other sections, mostly referring to 1N. | Included above | Included above | Included above | Included above
|  |  |  | Estimated Total Man-Hours to Complete Tenco Work Scope: | 4694
|  |  |  | Estimated Total Cost to Complete Tenco Work Scope: | 775320

## NYCT 8th Av - Tenco Proposal (hidden)
NYCT 8th Avenue CBTC S-48006 Contract Tenco Proposed Scope for CBTC EMC Program
Deliverables: | Per attached Tenco Task Matrix 8/28/2018
Tasks | Hours | Cost | Summary
0] EMC Project Management | 0 | 0 | Manage project and attend project review meetings
1] EMC Program | 0 | 0
#REF! | #REF! | #REF!
#REF!
Estimated Total Hours | 4694
Estimated Total Cost |  | 775320
Budget with Contingency |  | 930384 | Includes 20% Contingency
#REF!

## NYCT 8th Av EMC Scope Est. (hidden)
NYCT 8th Avenue CBTC S-48006 Contract Tenco Proposed Scope for CBTC EMC Program |  |  |  | David Turner | Andy Pattantyus | Linda Zausen | Eli Fernald | Brian McNally | Bernice Lopp | Ursula Monaghan | Brandon Whang | Carmine Daloia | Robert Gardner | Neil Shaw | Frank Nicholas | Stephane Yu | Noah Jones | Jon Luedeke | Steve Lawrence | Ross Holmstrom | George Soules | William MacCombie | Andrew Dombek | Trip | Night | Misc. | Total Hours | Cost | Task Total Cost | Total Hours
|  |  | Rate/Hr | 250 | 195 | 175 | 220 | 125 | 145 | 115 | 115 | 155 | 165 | 195 | 140 | 120 | 100 | 225 | 200 | 200 | 185 | 185 | 175 | 600 | 250
0] EMC Project Management
1] EMC Program
| 1.1.1 | EMC Control Plan (EMCP) |  | 40 |  |  | 40 |  |  | 60 | [5 empty] | 30 | [10 empty] | 170 | 29300
| 1.1.2 | EMI/EMC Management and Organizational Plan (EMOP) Provided as EMCP Appendix A. |  | 12 | 12 |  | 10 |  |  | 40 | [5 empty] | 10 | [10 empty] | 84 | 13340
| 1.1.3 | Design Implementation Plan (DIP) Provided as EMCP Appendix B. |  | 50 |  |  | 50 |  |  | 100 | [9 empty] | 50 | [6 empty] | 250 | 45000
| 1.1.4 | EMC Test Plan Provided as EMCP Appendix C. |  | 10 |  |  | 20 |  |  | 40 | [5 empty] | 20 | [10 empty] | 90 | 13900
| 1.1.5 | EMC Qualifications Provided as EMCP Appendix D. |  | 10 | 4 |  | 4 |  |  | 16 | 2 |  |  |  | 2 | 2 |  | 2 |  | 2 | 2 | [5 empty] | 46 | 7970
| 1.2 | Submittal Requirements | [24 empty] | 0 | 0
| 1.3 | EMC Design Report (EDR) |  | 20 | 50 |  | 40 | 100 |  | 80 | [5 empty] | 100 |  |  |  | 60 | [6 empty] | 450 | 69250
| 1.4 | EMC Signaling Compatibility Analysis (ESCA) |  | 40 | 30 |  | 40 |  |  | 80 | [5 empty] | 40 |  | 30 |  | 30 | 30 | [5 empty] | 320 | 56950
| 1.5.1 | EMC Factory Test Procedure |  | 10 |  |  | 40 |  |  | 60 | [7 empty] | 16 |  |  | 16 | [5 empty] | 142 | 24760
| 1.5.2 | EMC Factory Test |  | 10 |  |  | 20 |  |  | 20 | [16 empty] | 50 | 9200
| 1.5.3 | EMC Factory Test Report |  | 10 |  |  | 24 |  |  | 40 | [7 empty] | 8 |  |  | 8 | [5 empty] | 90 | 15660
| 1.6.1 | Track Circuit Test Procedures | [24 empty] | 0 | 0
| 1.6.2 | Track Circuit Test | [24 empty] | 0 | 0
| 1.6.3 | Track Circuit Test Report | [24 empty] | 0 | 0
| 1.7.1 | EMC Site Survey Procedure (ESSP) |  | 16 | 30 |  | 20 |  |  | 80 | [5 empty] | 40 |  |  |  | 20 | [6 empty] | 206 | 32250
| 1.7.2 | EMC Site Survey |  | 10 | 20 |  | 60 |  |  | 200 | [5 empty] | 200 | [9 empty] | 8000 | 490 | 74600
| 1.7.3 | EMC Site Survey Report |  | 16 | 20 |  | 20 |  |  | 60 | [5 empty] | 40 | [10 empty] | 156 | 24000
| 1.8.1 | Final Field EMC Test Procedure |  | 20 | 30 |  | 30 |  |  | 80 | [5 empty] | 60 |  | 16 |  |  | 16 | [5 empty] | 252 | 40410
| 1.8.2 | Final Field EMC Test |  | 16 | 20 |  | 160 |  |  | 200 | [5 empty] | 200 | [9 empty] | 8000 | 596 | 98100
| 1.8.3 | Final Field EMC Test Report |  | 20 | 20 |  | 20 |  |  | 60 | [5 empty] | 40 | [10 empty] | 160 | 25000
| 1.9 | EMC Safety Analysis (ESA) |  | 24 | 24 |  | 40 |  |  | 70 | [5 empty] | 70 |  | 35 |  |  | 35 | [5 empty] | 298 | 50280
| 1.10.1 | EMI/EMC Training Course |  | 30 | 30 |  | 50 |  | 200 | 100 | [5 empty] | 100 |  | 20 |  | 50 | 20 | [5 empty] | 600 | 95050
| 1.10.2 | EMI/EMC Training Video |  | 16 | 16 |  | 16 |  |  | 100 | [5 empty] | 40 |  | 16 |  | 24 | 16 |  |  |  |  | 12000 | 244 | 50300
|  | Total Misc. Cost | [23 empty] | 28000
|  | Total Hours | Hours Qty | 380 | 306 | 0 | 704 | 100 | 200 | 1486 | 2 | 0 | 0 | 0 | 2 | 992 | 0 | 143 | 0 | 236 | 143 | 0 | 0 | 0 | 0 |  | 4694
|  | Total Cost | Cost | 95000 | 59670 | 0 | 154880 | 12500 | 29000 | 170890 | 230 | 0 | 0 | 0 | 280 | 119040 | 0 | 32175 | 0 | 47200 | 26455 | 0 | 0 | 0 | 0 |  |  | 775320

## Proposal by Analyst (hidden)
NYCT 8th Avenue CBTC S-48006 Contract Tenco Proposed Scope for CBTC EMC Program
Deliverables: | Per attached Tenco Task Matrix
Assigned Staff:
Name | Hours | Rate/Hr. | Cost | Description
David Turner | 380 | 250 | 95000 | Engr. Director, Senior Technical Leadership
Andy Pattantyus | 306 | 195 | 59670 | Lead Analyst
Linda Zausen | 0 | 175 | 0 | Software and System Engineering
Eli Fernald | 704 | 220 | 154880 | Software and System Engineering
Brian McNally | 100 | 125 | 12500 | Software and System Engineering
Bernice Lopp | 200 | 145 | 29000 | Software and System Engineering
Ursula Monaghan | 1486 | 115 | 170890 | Software and System Engineering
Brandon Whang | 2 | 115 | 230 | Software and System Engineering
Carmine Daloia | 0 | 155 | 0 | Rail systems communications
Robert Gardner | 0 | 165 | 0 | Rail systems communications
Neil Shaw | 0 | 195 | 0 | Rail systems communications
Frank Nicholas | 2 | 140 | 280 | Safety System Design and Verification
Stephane Yu | 992 | 120 | 119040 | Safety System Design and Verification
Noah Jones | 0 | 100 | 0 | Safety System Design and Verification
Jon Luedeke | 143 | 225 | 32175 | Safety System Design and Verification
Steve Lawrence | 0 | 200 | 0 | Safety System Design and Verification
Ross Holmstrom | 236 | 200 | 47200 | ATC Software Safety
George Soules | 143 | 185 | 26455 | ATC Software Safety
William MacCombie | 26455 | 185 | 0 | ATC Software Safety
Andrew Dombek | 0 | 175 | 0
Estimated Labor Total | 4694 |  | 747320
Other Direct Cost: |  |  | Cost | Description
Trip |  |  | 0 | Flights to Toronto for meetings/testing
Night |  |  | 0 | Hotels in Toronto for meetings/testing
Misc |  |  | 0 | Equipment for EMC Tests
Estimated ODC Total |  |  | 0
Estimated Total Cost |  |  | 0
Total Not to Exceed Price |  |  | 0 | Includes 20% Contingency
Notes: 1] The Tenco planned scope and estimate is based on Tenco's recent past work experience on similar projects. 2] The estimate does not include contingency. 3] The Estimate does not include Track Circuit Test Procedures.