## Task Matrix
Melco M7 Propulsion System Overhaul Tenco EMC Task Matrix June 28, 2024
Task No. | Work Item | Submittal Date | Tenco Scope | Mitsubishi Electric Corporation (MELCO) Scope | LIRR / MNR Scope | Comments / Assumptions
1. Project Meetings, PDR and FDR
1.1 | Project Meetings | NA | Participate in PDR and FDR meetings, as directed. Prepare EMC Program Approach presenation for PDR. Provide more detailed EMC Program presentation for FDR, if necessary. | Coordinate, direct, and attend meetings, and invite Tenco as needed. | Participate in project meetings as necessary | Tenco proposal assumes 12 meetings for project management over 24 months. Tenco will provide 2 engineers to attend each meeting, and to attend PDR and FDR meetings in-person at LIRR Hillside yard.
2. EMC Document Updates
2.1 | EMC Control Plan (EMCP) [CDRL] | 2024-08-16 | Draft simple propulsion EMCP, describing relevant EMC issues for the overhaul. The EMCP will be much shorter than the prior M7 EMCP or the M9 EMCP due to the limited EMC impact of the overhaul. The EMCP will describe: * Relevant hardware and software changes for EMC * Field EMI test outline/plan * ESA approach * Exclusion of RE, CSI, TMIE tests Revise EMC Documents according to comments from Melco and LIRR / MNR. | Provide Tenco with requested documents and information on propulsion design. Review and comment on EMCP. | Review, comment on, and accept EMCP. | Proposal assumes Tenco will only provide EMCP and ESA. ESA will be provided as an appendix to the EMCP. Tenco will reference the original versions of the following documents in the EMCP: * EMI Technical File Summary * Electrical Model of the High Voltage Section. Tenco will not update these 2 documents, and will work with Melco to explain why they are not needed to LIRR/MNR. Per Melco RFP, Tenco will bear costs requiring document correction which are solely due to errors by Tenco, and not related to comments from LIRR / MNR, compressed schedule, or wrong or missing information. Tenco assumes no more than 2 rounds of revisions will be needed for the EMCP / ESA document to obtain LIRR and MNR approval.
2.2 | EMI Safety Analysis (ESA) [CDRL] | 2024-08-16 | Draft simplified propulsion ESA, providing assessment of EMI hazards and mitigations due to design changes from the original M7 propulsion design. Provide ESA as an appendix to the EMCP. Refer to original M7 ESA, and only updated ESA to determine the impact on EMI for: * Updated failure rate of the new capacitor * Updated failure rate of IGBTs and Line FIlter Inductors * BSR and OVCRf removal. | Provide updated capacitor, IGBT, and Line Inductor failure rates at LIRR, and other technical design information requested by Tenco. Review and comment on ESA. | Review, comment on, and accept ESA.
3. Vehicle-Level EMI Tests
3.1 | EMI Field Test Procedure (EFTP) [CDRL] | 2024-08-16 | Draft EFTP to measure worst-case conditions for CE and IE only. Revise EFTP per Melco and LIRR / MNR comments. | Provide requested technical information. Review EFTP and provide comments. Submit EFTP to LIRR / MNR. | Review, comment on, and accept EFTP | Tenco proposal assumes EMI Field Tests will only include vehicle-level IE and CE test. Melco's proposed design does not change the inverter box, PCU controller or wiring harness with traction motor. So, Melco's proposed inverter design change will not impact Cab Signal Interfernce (CSI) or Radiated Emissions (RE) test results. Tenco proposal does not include CSI, TMIE, or RE tests. Tenco assumes no more than 2 rounds of revisions will be needed for the EFTP document to obtain LIRR and MNR approval.
3.2 | Perform Pilot Married Pair Commissioning EMI Field Tests | TBD | Provide test engineers and equipment for IE and CE tests. Perform EMI Field Tests at LIRR, unless MNR requires testing at MNR also. Coordinate test schedule, test location, and LIRR resources with Melco, LIRR. | Provide regular status updates on test schedule, and provide at least 1 month notice for equipment preparation. Coordinate with LIRR / MNR for use of track, train maintenance and operating crews, yard use, shop use, test track time, logistics, security, access, and supervision Provide M7 staff including technicians to support EMI Field Tests | Provide staff and facilities to enable efficient EMI tests: * Access to track, yard, shop, mainline, EMUs, and other facilities * Test operators and maintenance staff as needed to perform tests * Signal and wayside support, including flaggers, as necessary * Clearance for testing on mainline * Track coordination meeting authorization * Communications & Security * Safety Training. Designate test track and provide description including mile marker location | Proposal assumes Tenco will only perform CE and IE tests. Proposal assumes Tenco will provide TransDAS smart stripchart recorder for M7 vehicle signals (e.g. speed, DC line current and voltage, tractive effort, etc...) Cost estimate assumes Tenco will provide 3 test engineers for 5 days or nights, with 10 working hours per day, including travel to/from test location, with at least 5 usable test hours per day or night. Cost estimate inlcudes 1 contingency test night. Estimate assumes overhauled vehicle CE and IE will be similar to the CE and IE measured during the M7 Regen Test performed by Melco and Tenco, and will be accepted by LIRR and MNR. Assumes online safety training.
3.3 | EMI Field Test Report (EFTR) [CDRL] | TBD | Draft EFTR, and submit for review. Revise per Melco and LIRR/MNR comments | Review EFTR and provide comments. Submit EFTR to LIRR/MNR | Review, comment on, and accept EFTR | Tenco assumes no more than 2 rounds of revisions will be needed for the EFTR document to obtain LIRR and MNR approval.
3.4 | Option: Original M7 VVVF Baseline EMI Levels Test | TBD | Provide test engineers and equipment to measure Original M7 VVVF baseline EMI levels at LIRR, unless MNR requires testing at MNR also. Coordinate test schedule, test location, and LIRR resources with Melco, LIRR. Compare the Original M7 VVVF baseline EMI levels with the upgraded inverter box levels. Update the EFTR. | Coordinate with LIRR / MNR for use of track, train maintenance and operating crews, yard use, shop use, test track time, logistics, security, access, and supervision Provide M7 staff including technicians to support the Baseline EMI Levels Test. | Provide staff and facilities to enable efficient EMI tests: * Access to track, yard, shop, mainline, EMUs, and other facilities * Test operators and maintenance staff as needed to perform tests * Signal and wayside support, including flaggers, as necessary * Clearance for testing on mainline * Track coordination meeting authorization * Communications & Security * Safety Training. Designate test track and provide description including mile marker location | Proposal assumes Tenco will only measure Original M7 VVVF baseline EMI levels. Proposal assumes Tenco will provide TransDAS smart stripchart recorder for M7 vehicle signals (e.g. speed, DC line current and voltage, tractive effort, etc...) Cost estimate assumes Tenco will provide 3 test engineers for 4 nights, with 10 working hours per day, including travel to/from test location, with at least 5 usable test hours per night. Cost estimate inlcudes 1 contingency test night. Cost estimate assumes Tenco will update the EFTR with the Baseline EMI Levels Test results.

## Cost Estimate
Melco M7 Propulsion System Overhaul Tenco Cost Estimate July 5, 2024
Task Item No. | Task |  | David Turner | Eli Fernald | Mike Thornburg | Ursula Monaghan | Stephane Yu | Temba Mateke | Pete Tabolt | Trip | Nights | Misc Rent Lab Rent Equip |  | Hours | Total Hours | Cost
|  | Rate/Hr | 325 | 300 | 180 | 150 | 130 | 120 | 250 | 1000 | 300
1. Project Meetings (incl. PDR and FDR) (Base) | [14 empty] | 80 | 20140
1.1 | Project Meetings |  | 8 | 30 |  | 30 |  | 12 |  | 2 | 2 |  |  | 80 |  | 20140
2. EMC Document Preparation (Base) | [14 empty] | 225 | 35635 | old total hours | hours reduction
2.1 | EMC Control Plan (EMCP) [CDRL] |  | 4 | 8 |  | 40 |  | 55 | [5 empty] | 107 |  | 16300 | 134 | 20.15%
2.2 | EMI Safety Analysis (ESA) [CDRL] |  | 3 | 10 |  | 40 |  | 53 | 12 |  |  |  |  | 118 |  | 19335 | 147 | 19.73%
3. Vehicle Level EMI Tests (Base) | [14 empty] | 410 | 78665
3.1 | EMI Field Test Procedure (EFTP) [CDRL] |  | 2 | 10 |  | 10 |  | 47 | [5 empty] | 69 |  | 10790 | 86 | 19.77%
3.2 | Perform Pilot Married Pair Commissioning EMI Field Tests |  | 3 | 60 | 15 | 70 | 25 | 70 |  | 2 | 14 | 1000 |  | 243 |  | 51025
3.3 | EMI Field Test Report (EFTR) [CDRL] |  | 2 | 16 |  | 60 |  | 20 | [5 empty] | 98 |  | 16850
Option Scope:
3.4 | Option: Original M7 VVVF Baseline EMI Levels Test |  | 2 | 65 | 10 | 65 | 20 | 65 |  | 2 | 14 | 1000 |  | 227 | 227 | 49300
Total Work |  | Hours | 24 | 199 | 25 | 315 | 45 | 322 | 12 | 6 | 30 |  | Total Base Scope Hours: | 715
[13 empty] | Option Scope Hours: | 227
[15 empty] | Total Base Cost: | 134440
[15 empty] | Option Cost: | 49300
|  | Cost | 7800 | 59700 | 4500 | 47250 | 5850 | 38640 | 3000 | 6000 | 9000 | 2000 |  |  | Total Cost (Base + Option): | 183740 | 183740
cost reduction
[12 empty] | Old Base Scope with FAR31 |  | 177817 | 24.39%
[12 empty] | Old Option Scope with FAR31 |  | 58906 | 16.31%
[12 empty] | Old Total Scope with FAR31 |  | 236723 | 22.38%

## Assumptions
Melco M7 Propulsion System Overhaul Tenco General Assumptions
1 | Tenco will perform the work on a time & material (T&M) basis. Tenco will not exceed the budgetary cost estimate without Melco authorization
2 | Tenco's scope consists of tasks and deliverables in the attached Task Matrix, consistent with Melco requirements. Tenco is available to perform additional Melco EMC / EMI work, as requested
3 | This cost estimate assumes that tasks flow smoothly and that test results are acceptable to LIRR / MNR. The proposed scope doesn't cover retest, delays, or supporting actions if LIRR / MNR doesn't accept test results
4 | Estimated total does not include contingency. Tenco recommends Melco reserve a 20% contingency
5 | Melco will approve the level of detail needed to satisfy LIRR / MNR requirements
6 | If more detail is required by Melco, LIRR, or MNR than covered by Scope for CDRL development, Tenco will prepare an expanded Scope and Estimate for Melco approval and budget authorization
7 | As directed by Melco, Tenco based this scope estimate on project activities over a 2 year period, starting in June 2024
8 | Tenco will track labor by month and invoice Melco monthly. Tenco will bill travel and equipment rental at cost
9 | The budget assumes Melco promptly provide documents upon Tenco request.
Note: The "Comments / Assumptions" column in the Task Matrix shows task-specific assumptions.