## Task Matrix
Turner Engineering Corporation Kawasaki Rail Car EMI Footprint Tests for LIRR M-9 EMUs
2022-09-28
Task No. | Work Item | Tenco Scope | Kawasaki Rail Car (KRC) Scope | Propulsion Supplier Scope | LIRR Scope | Notes
1. Review EMI Footprint Test Procedure and Test Preparation
1.1 | Review KRC EMI Footprint Test Procedure (EFTP) and Test Preparation | Join teleconferences and correspond with KRC and LIRR as needed to prepare for EMI Footprint Tests Review draft KRC EFTP and LIRR comments, and provide comments to KRC Review 2018 M-9 EMI qualification test results, and recommend worst-case conditions to test in the limited EMI Footprint test. Develop day-to-day test schedule. | Provide overall management of Footprint Test Schedule and attend Teleconferences, provide schedule updates and project information to Tenco Update EFTP and revise per Tenco and LIRR comments. Provide EFTP to LIRR Provide EMC program direction. | Provide documentation requested by Tenco. | Attend Teleconferences as required, provide LIRR input throughout project Review, comment on, and approve EFTP.
2. EMI Footprint Test at LIRR
2.1 | EMI Footprint Test at LIRR | Attend LIRR ROW Safety Training Provide test staff and test equipment to perform CE, IE and CSI tests at the LIRR sites selected by LIRR, KRC, and Tenco Coordinate test schedule with KRC. | Ensure M9 railcars to be tested are in good operating condition Coordinate with LIRR for use of track, train maintenance and operating crews, yard use, shop use, test track time, logistics, security, access, and supervision Provide M-9 staff including technicians for the EMI Footprint Tests. | Propulsion System supplier provide on-call, remote engineering staff to support EMI Footprint tests, as needed. | Provide Safety Training Schedule and provide: * LIRR facilities, access, staff including yard track usage and mainline access if needed * Operating and maintenance staff * Signal operations to turn off selected track signals during the test and to connect test equipment to rails if needed; * Safety and flagging * Logistics and coordination. For CSI calibration, provide ATC cab signal cal loop and cal box Schedule, provide direction, and provide LIRR engineer to witness the EMI Footprint Tests. | Tenco will measure CE, IE and CSI onboard and on the wayside of a LIRR Yard track during daytime hours Proposal assumes 4 test days, 1 contingency day: * 2 day for CE * 1 day for IE * 1 day for CSI. Schedule and budget assume 8 useful test hrs per test day, and all test days are consecutive Assume 4 hours of online safety training for LIRR ROW for 3 Tenco test staff Test Track wayside area requirements for IE and CSI calibration tests: Safe space for the test team to setup a test van or a table and chairs with shelter from rain, snow, wind and sun Test train requirements: Provide onboard PTU during the test, and coordinate with LIRR to operate M-9 train in ATC bypass mode during test. LIRR and KRC will coordinate AW3 physical loading, or simulated propulsion software for AW3 powering and braking tractive effort Tenco will provide a configured TransDAS If needed, as added scope, work with KRC and suppliers to resolve EMI issues shown in tests.
3. Provide Data and Comment on EMI Footprint Test Report
3.1 | EMI Footprint Test Report (EFTR) | Provide KRC EMI Footprint test data and graphs for the EFTR. Provide test summary email for each test performed Review the KRC drafted EFTR and provide comments to KRC Advise KRC as needed to get test report approval. Provide draft responses to LIRR comments and letter reviews. | Draft the EFTR and provide to Tenco for review. Integrate Tenco comments into the EFTR Submit EFTR to LIRR for review, and respond to LIRR comments. | None. | Review, comment on, and approve EFTR.