## TM Oct 2023
TISS Electric Locomotive (EL) for Taiwan Railways Administration (TRA) Tenco Proposed Scope for EL EMC Program | [6 empty] | Total Proposal Estimate
Turner Engineering Corporation (Tenco), October 25, 2023 Terms: Tenco proposes to perform the work on a time and material rate, at our engineering service rates in effect at the time. This proposal represents Tenco's estimated level of effort to support the schedule of activities provided by TISS. Tenco will bill for actual time and materials. Factors outside of Tenco's control can affect the actual level of effort. Tenco will stop work when the amount of TISS PO is reached, therefore TISS should include contingency funding above this estimate to prevent work interruption.
EL EMC Program Task Matrix
Task Item | Work Item | Tenco Scope | Tenco Deliverables | TISS Scope | TRA Scope | Comments / Assumptions | Estimated Task Cost
1] EMCP Task (not proposed since EMCP was developed by Toshiba)
1.1 | EMC Control Plan (EMCP) Rev 0 | 1] Provide EMCP outline to TISS. 2] Review draft EMCP and provide comments, as directed by TISS. |  | Provide requested documentation to Tenco to create EMCP. Review and comment on EMCP. Develop EMC Control Plan (EMCP) that covers project EMC requirements, actions, and deliverables. Submit EMCP to TRA. Provide TRA comments on EMCP to Tenco. Distribute EMCP to equipment suppliers. Coordinate with suppliers to meet the EMCP requirements. | Review and comment on EMCP. | EMCP Rev 0 will provide program overview including requirements, tests, and design criteria. EMCP Rev 2 will provide in depth EMC design techniques and control measures such as interleaving, grounding, and shielding, standard EMI techniques. In October 2019 Tenco suggested that EMCP Rev 0 include: * EMC Requirements * Schedule of EMC document submissions and milestones * EMC tasks * EMC technical design requirements * EMC Test Plan section, including: * Test procedure and report requirements * EL-level Conducted Emissions (CE), Radiated Emissions (RE) per EN 50121-3-1, and Magnetic Field tests * DC Inrush Test. This scope assumes no Tenco responsibilities for DC inrush test. * Equipment Emission and Immunity tests per EN 50121-3-2. * Name, address and relevant certification of any EMI/EMC Test Laboratory planned for the project. * Other TRA TS or TISS-specific EMI/EMC information. Estimate assumes: * ATC/ATP is equivalent to TEMU. * There will be a propulsion system lab test. * Tenco has no responsibilities for propulsion system, APS and subsystem lab tests. * Submission will include English and Chinese in side by side pages. Tables will include translation in each cell. TISS provides Chinese translation.
1.2 | EMC Control Plan (EMCP) Rev 1 | 1] Discuss EMC control measures and propulsion and APS inverter interleaving scheme with TISS engineers 2] As directed by TISS, revise EMCP to include discussion of design details and EMC control measures 3] As directed by TISS, revise EMCP per TISS and TRA review comments on initial submission. |  | Answer Tenco questions regarding EMC control measures and interleaving scheme. Provide documentation requested by Tenco. Review and comment on EMCP. Submit EMCP to TRA. Provide TRA comments on EMCP to Tenco. Distribute EMCP to equipment suppliers. Coordinate with suppliers to meet the EMCP requirements. | Review and comment on EMCP. Approve EMCP. | Tenco understands the following sequence for EMCP Rev 1: 1] TISS made EMCP Rev 0 submission (NTP +30 days) 2] As directed, Tenco provide comments on content and needed technical info 3] TISS submits EMCP Rev 1 to TRA (scheduled for NTP +120 days) Tenco cost estimate assumes: * TISS updates Chinese translation for Rev 1 * ATC/ATP is equivalent to TEMU. * Toshiba will perform propulsion system lab test. Tenco scope does not include plan, performance, or attendance at Toshiba propulsion system lab test.
2] EL EMC Test Procedures
2.1 | EL EMC TISS Factory Test Procedures Rev 0 | Draft TISS Factory Test Procedures for RE and CE. Draft additional section for routine test requirement to check DC input current. Submit TISS Factory Test Procedures to TISS for review. |  | Provide information on TISS Factory Test arrangements, test track, test procedures, test track schedule. Review and comment on test procedures drafted by Tenco. | Review and comment on TISS Factory Test Procedures. | Estimate assumes for all procedures and reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation.
2.2 | EL EMC TISS Factory Test Procedures Rev 1 | Revise TISS Factory Test Procedures per TISS and TRA review comments on Rev 0. Submit TISS Factory Test Procedures to TISS for review. |  | Provide information on TISS Factory Test arrangements, test track, test procedures, test track schedule. Review and comment on test procedures drafted by Tenco. | Review and comment on the TISS Factory Test Procedures. Approve TISS Factory Test Procedures. | Estimate assumes for all procedures and reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation.
2.3 | EL EMC TRA Field Test Procedures Rev 0 | Draft TRA Field Test Procedures for depot CE test and mainline RE, CE, and magnetic field tests. Draft additional section for Depot (pit line) tests. Submit TRA Field Test Procedures to TISS for review. |  | Provide information on TRA Field Test arrangements, test track, test procedures, test track schedule. Review and comment on test procedures drafted by Tenco. | Review and comment on the TRA Field Test Procedures. | Estimate assumes for all procedures and reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation.
2 | Project Management and test planning for Tasks 2 and 4 RFQ# Pending PN: Pending | Interface with TISS project management. Field Test Planning and Scheduling. Tenco internal project management.
2.4 | EL EMC TRA Field Test Procedures Rev 1 RFQ# F212E0297774 PN: PN-KH8230013630 | Work as directed by TISS to resolve TRA comments on Rev 0 of the procedure and gain TRA approval of Rev 1. | 1. Email responses to TISS questions related to the test procedure. 2. If directed by TISS: EL EMC Field Test Procedure, Rev 1 (English, in MS Word). 3. If directed by TISS: If directed by TISS: EL EMC Field Test Procedure, Rev 1 (Chinese, in MS Word). | Provide information on TRA Field Test arrangements, test track, test procedures, test track schedule. Interface with TRA. Provide direction to Tenco. | Review comment on the TRA Field Test Procedures. Approve TRA Field Test Procedures. Commit to provide any TRA dependencies identified in the approved test procedure. | Estimate assumes for all procedures and reports: * Tenco delivers both English and Chinese versions in separate MS Word documents.
3] EL EMC TISS Factory Test and Test Report
3.1 | EL EMC TISS Factory Test (complete locomotive) RFQ# PA0903846 PN: PN-KH8230003061 | Provide test staff and test equipment to perform TISS Factory Test consisting of low speed RE and CE tests per EN 50121-3-1 and routine test to check DC input current. Perform tests and collect data. Work with TISS and suppliers to resolve EMC issues resulting from test. |  | Provide management, scheduling, customer coordination, and guidance for tests. Provide test track, EL and traction power. Provide technical staff to install test equipment. Provide technical and test staff to operate EL as needed for tests. | Witness the TISS Factory Test and provide direction. | Tenco assumes 9 available hours of testing on test track for each day at TISS Factory. Limited access to track or difficult testing conditions that reduce available testing hours may require more test days than estimated. Refer to "TISS Fuchu Factory EMI Test Schedule" for the daily activity. The test is 5 working days plus 2 contingency days. Tenco test plan requires 3 test engineers. Tenco assumes 11 hour days for test engineers for each day of factory test consisting of 1/2 hour morning meeting + 9 hours testing + 1/2 hour daily wrap-up meeting + 1 hour daily data review. Two contingency days are included in the base schedule for ordinary contingencies, based on Tenco's past experience. Factors outside of Tenco's control may cause additional test delay. Examples of such factors include: * Locomotive not operable * Test track power or rail condition does not allow for test runs to be made * Interference from JR trains invalidates test runs Tenco budget estimate assumes full engineering test. Estimate assumes TRA witness will be present during full engineering test. A separate witness test may require more test days and affect scope estimate. Estimate assumes TISS provides translator staff for factory tests. Note: Travel between US and Japan assumes Premium Economy rate, or if unavailable, Business Class. Travel within Japan assumes Shinkansen ordinary car, reserved seat. Tenco budget does not include Magnetic Field Tests at TISS Factory because low test speeds mean low power thus low Magnetic Field readings.
3.2 | Preliminary Test Report RFQ# PA0904646 PN: PN-KH8230003770 | Prepare Preliminary Factory Test Report. This report will be provided in English only. |  | Provide office space with internet. | Not required. | The preliminary report will be prepared while the test team is located in Fuchu. This allows for Toshiba to provide immediate input in real time.
3.3 | EL EMC TISS Factory Test Report Rev 0 RFQ# PA0903847 PN: PN-KH8230003050 | Prepare TISS Factory Test Report, using test data collected during Field Tests. Submit TISS Factory Test Report to TISS for review Provide Test Data files per EMCP 10.9. | 1. EL EMC Factory Test Report Rev 0 (English, in MS Word). 2. EL EMC Factory Test Report Rev 0 (Chinese, in MS Word). | Review and submit TISS Factory Test Report to TRA. | Review and comment on the TISS Factory Test Report. | Task 3.3 is authorized by Toshiba PO F212P0290717. Tenco understands that TRA has requested that TISS deliver the Factory Test Report based on data collected during the Field Testing Tenco budget estimate assumes for all reports: * Tenco delivers both English and Chinese versions in separate MS Word documents. | Toshiba PO F212P0290717.
3.4 | EL EMC TISS Factory Test Report Rev 1 RFQ# Pending PN: Pending | Work as directed by TISS to resolve TRA comments on Rev 1 of the Factory Test Report and gain TRA approval of Rev 1. | 1. Email responses to TISS questions related to the test report. 2. If directed by TISS: EL EMC Factory Test Report Rev 1 (English, in MS Word). 3. If Directed by TISS: EL EMC Factory Test Report Rev 1 (Chinese, in MS Word). | Interface with TRA. Provide direction to Tenco | Review comment on the TISS Factory Test Report. Approve TISS Factory Test Report. | Scope Matrix assumes EL passes all TISS Factory Test. Tenco budget estimate assumes for all reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation. | Not included in PO F212P0290717. Remaining budget is likely sufficient.
4] EL EMC TRA Field Test and Test Report
4.1 | EL EMC TRA Field Test RFQ# F212E0297774 PN: PN-KH8230013590 | Perform testing as defined the approved Factory and Field test procedures, working in collaboration with TISS staff, and in accordance with TISS's schedule. Perform retests or procedure defined test procedures if necessary. | 1. Rental, logistics and shipping of test equipment from the US to a location and individual (receiver and consignee) in Taiwan, as designated by TISS. 2. Test staff to perform testing in accordance with the approved Field Test Procedure at locations in Taiwan as designated by TISS, and in compliance with TRA reqirements such as safety training and health examinations. 3. Senior staff support from the US and Japan. 4. Test staff travel from US to Taiwan and within Taiwan as needed to support the TISS schedule. 5. Test staff accommodation and meals in Taiwan at locations designated by TISS. 6. Logistics and shipping of test equipment from Taiwan to the US as the conclusion of testing. | 1. Provide management, scheduling, customer coordination, and guidance for tests. 2. Coordinate with TRA for use of Depot/Pit-line and mainline track, train maintenance and operating crews, yard use, shop use, track time, logistics, security, access, and supervision. 3. Provide EL for testing. 4. Logistics and shipping of test equipment within Taiwan as needed to support testing at multiple test sites. 5. Provide a portable 100 volt or 110 volt 60 Hz generator to power the test equipment. 6. Provide tent, table, chairs etc. at test locations. 7. Provide secure storage for test equiment. | Approve test dates and locations. Schedule and provide TRA facilities, access, staff including yard track usage and mainline access if needed; operating and maintenance staff; safety and flagging; logistics and coordination. Provide Witness for TRA Field Test. | Tenco's estimate is based on testing per the TISS schedule as provided via email on October 5 and the following assumptions: * The test team in Taiwan will be 2 persons for Low Speed tests and 4 persons for High Speed Tests. * Test team in Taiwan works for 10 hours per day for each scheduled test and contingency day. * Test team in Taiwan will bill 8 hours for each day associated with the TRA required health check. * Test team in Taiwan will bill 1 hour each for TRA safety training. * Senior staff provides support for 2 hours per day for each scheduled test day. * Test team in Taiwan does not bill scheduled weekend end non-test days to Task 4.1. Team members may bill Tasks 3.3, 4.2 and 4.4 on these days. * International travel requires 16 hours each way. * Test team in Taiwan will make one round-trip between Taipei and Tainan, requiring 8 hours. Note: International travel assumes Premium Economy rate, or if unavailable, Business Class. Lodging and meals at US State Department published per diem.
4.2 | EL EMC TRA Field Test Report Rev 0 RFQ# F212E0297774 PN: PN-KH8230013620 | Prepare EMC Field Test Report. Submit Field Test Report to TISS for review. Provide Test Data files per EMCP 10.9 and 10.10 |  | Review and submit TRA Field Test Report to TRA. | Review and comment on the TRA Field Test Report. | Scope Matrix assumes EL passes TRA Field Test. Tenco budget estimate assumes for all reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation.
4.3 | EL EMC TRA Field Test Report Rev 1 RFQ# Pending PN: Pending | Update TRA Field Test Report per TISS and TRA comments. Submit TRA Field Test Report to TISS for review. Revise per additional comments, if necessary. |  | Review and submit TRA Field Test Report to TRA. | Review comment on the TRA Field Test Report. Approve TRA Field Test Report. | Scope Matrix assumes EL passes TRA Field Test. Tenco budget estimate assumes for all reports: * Submission will include English and Chinese versions as separate documents. * Tenco provides Chinese translation.
4.4 | Resolution of EMC issues identified during testing. RFQ# Pending PN: Pending | As directed by TISS: Perform Ad-hoc tests to resolve issues during field tests. Provide technical support to TISS's equipment vendors. | As directed by TISS | Interface with TRA. Provide direction to Tenco |  |  | As directed by TISS